## Slide 1: Integrated Performance Report (IPR)
Dec 2024

## Slide 2: NICE Guidance highlights
Reducing heart failure hospitalisations by recommending
2 algorithm-based monitoring technologies that detect and notify early signs of worsening heart failure.
Reducing symptoms of
Chronic tic disorders and Tourette syndrome in children and young people by recommending 2 technologies - the first recommended digital technologies for these disorders.
Improving the diagnosis and management of endometriosis,
a condition that affects approximately 1.5 million women in the UK, with updated guidance published.
Supporting NHS performance through the analogue to digital shift
Improving people’s health
Driving faster access to innovation and supporting industry
New findings show that NICE
Advice’s scientific advice service can reduce appraisal timelines by nearly 3 months.
Latest figures show a
17% improvement in timeliness of medicines appraisals*
Improving fracture
detection rates in urgent
care by recommending the use of 4 AI tools to help detect fractures.
Figures show that the largest
number of people on record
are benefitting from NICE-recommended statins to reduce heart attacks and strokes following our updated guidance.
Latest figures show a
19% improvement in timeliness of health tech appraisals **
*Measured as the mean time between marketing authorisation for medicines and NICE recommendation, YTD compared to 23-24 performance
** Measured as the mean time to publish HealthTech guidance, YTD compared to 23-24 performance

## Slide 3: Dec 2024 IPR contents page
Section | Slide / chart number | Lead
Executive summary – highlights and escalation points | 4 | All ET
Summary of performance – Relevance | 5-6 | Jonathan Benger
Summary of performance – Timely and high quality | 7-9 | Sam Roberts
Summary of performance – Usable | 10-11 | Clare Morgan
Summary of performance – Demonstrable Impact | 12-13 | Clare Morgan
Summary of performance – Organisational Brilliance | 14-15 | Helen Brown
Finance | 16 | Pete Thomas
Appendix to Brilliant Organisation | 17-18 | N/A - appendix
Headline description of key projects | 19 | N/A - appendix

## Slide 4: Executive summary on NICE Business Plan progress 2024-25 (Dec 2024)
Area | Current Status | Key highlights and successes | Key challenges
Focusing on What is Most Relevant | Green | The external stakeholder consultation on HST routing criteria starts on 19 December until 30 January (having been through extensive internal and external stakeholder engagement) Early feedback on the menopause guideline download data suggests that users are accessing the ‘menopause discussion guide’ (2nd only to the guideline pdf). The opening speech by NICE's CMO at the 'Guidelines Live' conference covered areas that focused on creating guidance that is most relevant to the system. The clinical directorate is proactively engaging with the Royal Colleges to discuss 'NICE Collaboration' – which facilitates partnership working through 6 approaches for guideline development. Enhanced horizon scanning capability is improving with an ultra-orphan scan completed to support the revised HST criteria and a cross-functional advisory board planned in December/early January to refine outputs in relation to high-profile/complex topics. | Capacity in the pipeline of guidance producing teams to start developing the topics prioritised by the prioritisation board. Complexity of clarifications sought following prioritisation decisions. Managing the number of requests that we are getting to amend, update or develop guidance, and how we deal with them. Deciding how we deal with ‘non-standard’ topics, such as those relating to Software as a Medical Device, or medical devices in general
Providing High Quality & Timely Advice | Green | Timeliness: All 4 project teams have hit the expected milestones to develop an aim and their theory of change and developing an initial set of prioritised change ideas to test. AMR (Medicines) and Interventional Procedures (HealthTech) topics the first to be launched in MS Project Online using the new modular timeline approach. Methods: External engagement on health inequalities finalised. Incorporation of TAs: On track to achieve in year target. | Timeliness: Additional work taking place to identify and standardise data that can be used to demonstrate improvement. Methods: Continuing to monitor the feedback from the severity modifier. Incorporation of TAs: Teams will begin to face capacity challenges as work intensifies. Rules Based pathway: Requires alignment with the 10 Year Health plan and spending review
Ensuring our Advice is Usable | Green | Workshop held in Dec with multi-disciplinary teams to ensure alignment with strategy and to develop short and medium-term workplans. Significant progress made with new structured recommendations and working with external partners on a semantic data model that will underpin a new knowledge platform. Refreshed plan driving delivery | With a change in workplans, a key challenge is to ensure delivery of shorter-term outputs while ensuring alignment of longer-term delivery with the new product strategy.
Demonstrable impact | Green | Completed work with partners around maternity insights. Uptake data directory updated with national data associated with the maternity topic. Prepared support to be released with tirzepatide TA and obesity guideline Completed review of NICE's Productivity & Health Inequalities pages, with agreement of next steps. Prepared summary for Board on NICE's role in relation to uptake and adoption of guidance (for December Board seminar) | Capacity to meet potential demand for implementation support in relation to release of final TA for tirzepatide Capacity impact of tirzepatide related support for the rest of the Impactful programme.
Brilliant organisation | Amber –forecast underspend​ exceeds target | Business Partnering work has commenced with external Organisational Development support to identify and roll out the model across all Support Functions at NICE. 'Managing Change Well' (MCW) workstream in place to improve on the associated work with current and future organisational design. ET briefed on current state and a plan is now in place to manage upcoming change as smoothly as possible. MCW toolkit being designed by People Team. Multichannel communications plan developed for NICE’s work in/with AI, >1,000 registrations already for webinar on 10 December. Leadership development in Healthtech, Medicines and CfG. We are updating the medium-term financial plan assumptions following the October Budget Statement and latest SR25 intelligence to inform business planning and budget setting for 2025/26. | Forecast underspend exceeds our KPI. Whilst there are some uncertainties, capacity constraints and spend controls mean that the underspend could increase by the end of the financial year. Capacity challenges within the People Function present a current challenge versus anticipated activity to deliver.
4

## Slide 5: Relevance: Exception report
RAG rating:
Green
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
Key activities for next month
Key risks and mitigants
Risk | I | L | S | Key Controls
Some developer teams could reach their capacity and be unable to take new topics from Prioritisation Board | 3 | 3 | 9 | Developing ways to explore relative priority of topics considered by the PB - looking at potentially using the voting scores to determine relative priority, but it may also be a matter of re-presenting prioritised topics to PB and then asking them to undertake a relative prioritisation exercise.
The Prioritisation Board could reach its capacity to work through and consider the volume of topic suggestions put forward | 3 | 3 | 9 | Refining implementation of stage 1 process to improve efficiency and sustainability as we learn more now the ‘suggest a topic’ function is in use. We have refined the process by embedding a review by Consultant Clinical Advisors before PB. They review the stage one briefings and the proposed prioritisation decision; PB then reviews those decisions.
Very low
Low
Medium
High
Very high
Prioritisation will be discussed at the December Board meeting.
GIAA audit of Prioritisation is in process.
The external stakeholder consultation on HST routing criteria starts on 19 December until 30 January.
Work continues on the mapping and identification of where NICE needs to focus to fully implement a safety management system (SMS) model as conceptualised by HSSIB.
Annual report on patient safety for discussion at the December Board.
The patient safety team is working with colleagues from HSSIB and other national bodies to support the development of a safety recommendations repository.
We have completed a retrospective HST routing decision impact analysis that considered the application of the new, refined HST criteria to previous routing decisions. This has confirmed that the purpose of the review is to add clarity, and has also demonstrated that the review is likely to be opportunity cost neutral overall.

## Slide 6: Relevance: High-level summary of performance
NICE Business plan KPIs | Actual YTD | KPI performance target 24-25 | KPI starting performance 23-24 | Trajectory
% of positive decisions made by the Prioritisation Board that align to the key NHS and social care priorities described in our annual Forward View | 67% | 90% | N/A – new measure | N/A – new measure from Oct 24
% of responses to Regulation 28 reports, HSSIB safety recommendations and safety alerts within specified and/or statutory timeframes | 100% | 95% | 90-95% | 
NICE Bus Plan Milestones | Due Date | RAG
Common prioritisation framework published following public consultation and agreement with system partners | Q1 | C
NICE’s Prioritisation Board launched | Q1 | C
Prioritisation Board’s forward look published | Q1 | C
Single horizon scanning function operational, linking with external providers | Q2 | A
Agreed an approach for recognising guidance from other organisations in areas where NICE does not produce guidance | Q2 | C
Consulted on any identified changes to routing criteria for Highly Specialised Technology Appraisals | Q4 | G
RAG rating key: C= complete; G= green; A= amber; R= red
Notes on RAG status:
1
2
3 positive decisions in October - 2 aligned with Forward View and priorities, 1 not aligned
All figures as of 31 Oct 2024 unless otherwise stated
1
2
Onboarding of new starters currently underway, should be complete by end of Q3

## Slide 7: Timely & High-Quality: Exception report
RAG rating:
Green
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
Improving timeliness of guidance production and staff experience:
Business case approved by the NICE Board in July 2024
Programme Manager role currently in development
Service owners and ET leads agreed for 3 of 4 initial services
Committee members surveyed on current practice and process 'pain points'
Late Stage Assessment:
First topic (TAVI) went to committee in July
Incorporation of TAs into guidelines:
Plan Do Study Act (PDSA) cycle took place in July. Lessons learnt from initial work
Next batch of incorporated TAs ready for sign off prior to publication
Rules Based Pathway
Joint NICE/NHSE/DHSC Steering Group, Working Group, and Task and Finish Groups have been established and are operational
NICE is leading on topic selection and NICE assessment. NICE has drafted hypotheses for how these processes need to be adapted and is iterating with other interested parties
Key activities for next month
Improving timeliness:
Teams to start testing change ideas.
To develop operational definitions of the outcome measures of the programme.
Process Hub set-up with example processes
Further learning sessions led by Institute of Healthcare Improvement to take place
Additional training events and communications for users of MS Project. Guidelines, HealthTech and Medicines preparing to formally implement MS Project Online for all remaining topic types
Methods:
Health inequalities modular update and supporting documentation to GE on 17th December
Progress internal commentary on societal preference work and draft proposal for DHSC R&D project on severity weighting
Incorporation of TAs: We have engagements with NICE Board in December and then ABPI in January where we need to consider the case for complex incorporation in advance of business planning.
Workstream | Risk | I | L | S | Key Controls
Improving timeliness | Some teams may constrain their thinking and change idea opportunity identification, which may lead to a lack of significant improvement without digital transformation. | 4 | 4 | 16 | Review of the Planning Tools business continuity to help alleviate worries and shift the focus from digital solutions.
Methods | NICE’s decision around the severity modifier is not understood and is continually challenged by stakeholders | 3 | 4 | 12 | Continual monitoring of the use of the severity modifier. Engagement on industry-funded societal preference work. Launch NICE Listens severity weighting project
Improving timeliness:
Interventional Procedures and Medicines team now using MS project for the planning of new and live topics.
All teams have developed their theory of change and a set of prioritised change ideas for testing.
Previous capacity issues being addressed with programme underspend.
Programme lead recruited and starting on 2nd December 2024.
Clarification reached around DIT support for changes and some core deliverables.
Methods:
Health inequalities modular update reviewed internally, and external stakeholder engagement completed
NICE Listens severity project tender drafted, and work commenced on internal commentary on industry-funded societal preference work
Incorporation of TAs: We are now on track to have published 113 TAs into guidelines by the end of Q3 against a plan of 120. December publications are all set to go out 19th December.
Rules based pathway: Work underway to re-focus and work out next steps for future work between NICE and NHSE
Key risks and mitigants
Very low
Low
Medium
High
Very high

## Slide 8: Timely & High-Quality: High-level summary of performance (1 of 2)
Notes on RAG status:
Plans for handling prospective incorporation are in place and this process will commence in Q3. This was delayed from Q1 due to planned TAs not being published.
Data being collected to establish baseline and further analysis required to bring this work back on track
NICE Board KPIs (this slide are all NICE Board level KPIs ) | Actual YTD (Mean) | KPI performance target 24-25 | KPI starting performance 23-24 | % improvement / decrease vs 23-24 performance
Medicines - Mean time between marketing authorisation and NICE recommendation (optimal and divergent) | 373 days (N=30) | Improvement on 23-24 baseline | 452 days | 17% Improvement
Medicines - Median time between marketing authorisation and NICE recommendation (optimal and divergent) | 332 days (N=30) | Improvement on 23-24 baseline | 322 days | 3% decrease
Medicines - Mean time between marketing authorisation and NICE recommendation (optimal) | 52 days (N=7) | 90 days | 36 days | Within target, but 44% above 23/24 mean
Medicines - Median time between marketing authorisation and NICE recommendation (optimal) | 49 days (N=7) | 90 days | 43 days | Within target, but 14% above 23/24 mean
NICE Board Milestones | Date | RAG
Start routinely incorporating relevant medicine technology appraisals in guidelines | Q1 | A
Understood baseline and opportunities for improvement in guidance producing processes | Q2 | R
Rolled out digital tools that support planning and identified future planning/scheduling needs | Q3 | G
Aligned and digitised some key steps in guidance producing processes | Q4 | G
Reviewed the use of the severity modifier in medicines evaluation and identified remedial actions if needed | Q2 | C
Updated methods for assessing health inequalities in guidance production | Q4 | G
Expanded HTA Lab capacity in line with new VPAG funding and delivered insightful outputs supporting high quality guidance | Q4 | G
Launched 8 Late-Stage Assessment topics | Q4 | G
Consulted (with NHSE) on a medtech rules-based pathway | Q1 | C
RAG rating key: C= complete; G= green; A= amber; R= red
1
1
All figures as of 31 Oct 2024 unless otherwise stated
2
2

## Slide 9: Timely & High-Quality: High-level summary of performance (2 of 2)
NICE Board KPIs (this slide are all NICE Board level KPIs ) | Actual YTD (Mean) | KPI performance target 24-25 | KPI starting performance 23-24 | % improvement / decrease vs 23-24 performance
Medicines - Mean time between marketing authorisation and NICE recommendation (divergent) | 471 days (N=23) | Improvement on baseline 23-24 | 540 days | 13% improvement
Medicines - Median time between marketing authorisation and NICE recommendation (divergent) | 494 days (N=23) | Improvement on baseline 23-24 | 365 days | 35% slower
Medicines - Percentage of optimal topics published in 2024/25 (year to date) | 23% | Improvement on 23-24 baseline | 17.5% | 5.5% point improvement
HealthTech - Mean time to publish HealthTech guidance | 396 days (N=15) | Improvement on 23-24 baseline | 490 days | 19% improvement
HealthTech - Median time to publish HealthTech guidance | 399 days (N=15) | Improvement on 23-24 baseline | 402 Days | 1% improvement
CfG – % of quality standard updates published alongside guideline updates | N/A | 30% | N/A | N/A
% of TAs retrospectively incorporated by end of 24/25 | 66% (N=113) | 33% (170 out of 517) | N/A | N/A
KPIs reflect Q1 figures; Two KPIs have not been included here:
1) “Mean and median time to produce new guideline and guideline update” - data is being captured to establish a baseline for future measurement in 25-26;
2) “New NICE guidance within topic suites published within 6 months of Prioritisation Board's decision to update” - baseline data will start to be collected from August, and will be captured on a quarterly basis
All figures as of 31 Oct 2024 unless otherwise stated

## Slide 10: Useable: Exception report
RAG rating:
Green
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
Structured recommendations: Work has started to develop a controlled vocabulary to be used for guidance recommendations. The focus of the controlled vocabulary is initially on the obesity and weight management guideline, which will be used to deliver a proof of concept to test with users. DIT are supporting this work by running an audit of the verbs currently used in guideline recommendations which will be used to inform the 'action' component.
Knowledge platform: NICE and AWS PACE team had first cadence meeting. The AWS team described their overall approach to technology set up and the steps that they will be taking. Initial weeks are centred in the underpinning technology infrastructure.
Key activities for next month
Workshop planned to review the Useable Product Strategy and co-design the outcomes and 2 year programme of work required to deliver agreed measures of success.
Structured recommendations: Further sprint planned to develop the vocabulary for other components. Planning for medicines and health tech recommendations to be reviewed by Guidance Executive on 9th December, with a plan for implementation being developed.
Knowledge platform: Consideration of multiple taxonomies and classifications services that will be explored during the project. Work on defining semantic models that can represent all our guidance and language models as much as possible.
Key risks and mitigants
Very low
Low
Medium
High
Very high
Workstream | Risk | I | L | S | Key Controls
Integration of foundational activities | Work packages to create a structured recommendations framework, content governance and the foundational work to develop a digital knowledge platform have been developed independently. Unless mitigated collectively there is a risk that our foundational work does not enable NICE to create innovative guidance products. | 3 | 3 | 9 | Refreshed delivery plan and outcomes to align with approved product strategy. Programme management of the useable programme to actively manage all foundational aspects, accountability, risk management, resource allocation and interdependencies for refreshed delivery plan. Recruitment of a Programme Lead to manage integration of activities.

## Slide 11: Useable: High-level summary of performance
Business plan KPIs | Actual YTD | KPI performance target 24-25 | KPI starting performance 23-24 | % Increase vs 23-24
No of users accessing NICE website for guidance and advice | 8.9 million (24/25 Year to Date) | Increase on equivalent calendar months from 23-24 | 7.3 million (23/24 Year to end-August) | +22%
 | As above | Increase on 23-24 | 18.278 million (Full year) | N/A
Clicks on guidance products from the NICE corporate website (monthly figures) | 35,000 (24/25 Year to Date) | 37,700 (15% increase from equivalent months in 23-24) | 32,800 (23/24 Year to end-August) | +7%
 | As above | 95,700 (15% increase in full year) | 83,200 (Full year) | N/A
Bus Plan Milestones | Due Date | RAG
Complete migration to new corporate website | 30 Dec 24 | A
Complete proof of concepts with semantic data model to inform next steps of knowledge platform | 1 July 24 (expected Q4) | A
Agree standardised wording and structure for recommendations | 31 Dec 24 | G
Launch a new content governance process for CHTE and CfG | 31 Dec 24 | G
RAG rating key: C= complete; G= green; A= amber; R= red
Notes on RAG status:
Clicks on products are higher than last year but not reaching the projected 15% increase for this year. There will be further promotion of guidance topics on the homepage to encourage more clicks.
Some remaining page components not built yet. Working with DIT to establish a dedicated project team focused on website migration and unpicking admin issues to allow the web team to fully access Storyblok.
The start date agreed with Amazon Web Services for the build phase is mid-October for a period of 12 weeks, so the delivery milestone has been amended accordingly.
1
3
All figures as of 31 Oct 2024 unless otherwise stated
2
1
2
3

## Slide 12: Impactful: Exception report
RAG rating:
Green
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
Uptake measurement
Completed work with partners around maternity insights. Uptake data directory to be updated with national data associated with the maternity topic.
Completed review of uptake of semaglutide and tirzepatide TAs.
Completed initial scoping with NHS England on respiratory guidance uptake and agreed opportunity for collaboration.
Completed and shared briefing for NICE colleagues that gather system intelligence on common implementation issues in Early Value Assessments.
Implementation support
Prepared support to be released with tirzepatide TA and obesity guideline
Completed review of NICE's Productivity & Health Inequalities pages, with agreement of next steps.
Prepared summary for Board on NICE's role in relation to uptake and adoption of guidance to inform the strategy (for December Board seminar)
Key activities for next month
Uptake measurement​
Final uptake insights to be agreed to support maternity implementation programme and plan to supply routine uptake insights for obesity
Develop draft KPI for proportion of priority guidance measures showing an improvement in national uptake
Actionable insights shared across the organisation based on quarter 2 system intelligence
Agree principles for structuring of data to provide improved system intelligence based on user feedback
Implementation support ​
Agree mock-up design of implementation support packages, with continued development of the obesity management and maternity packages
Completion of review of external networks to understand any overlaps and gaps
Completion of process for signposting to external resources
Review of archived shared learning case studies to understand which (if any) can be reinstated
Patient and community engagement
Key issues, risks and mitigants
Workstream | Risk | I | L | S | Key Controls
Implementation support | As a result of the launch of the Tirzepatide guidance in the current operating environment there may be implementation challenges resulting in reputational damage | 3 | 3 | 9 | Mitigation currently in place Implementation plan agreed Funding variation agreed
Very low
Low
Medium
High
Very high

## Slide 13: Impactful: High-level summary of performance
Business plan KPIs | Actual YTD | KPI performance target 24-25 | KPI starting performance 23-24 | Trajectory
Proportion of agreed priority guidance measures showing an improvement in national uptake (health and care system priority areas, populations with identified health inequalities, areas that matter most to people and the communities). | N/A | N/A | N/A Baseline to be established during 24/25 | N/A
All agreed priority areas have targeted implementation support package in place | 3 | 5 | 0 | 
New partnerships (including VCS organisations) to amplify the impact of NICE guidance in agreed priority areas. | 5 | 5 | 0 | 
Bus Plan Milestones | Due Date | RAG
Developed and implemented a fairer payment policy for involvement and engagement activity | 21 June 24 | C
Routine reporting of prioritised uptake measures in place | 31 July 24 | C
Joint plans in place to amplify the impact of NICE guidance through priority partnerships | 30 Sept 24 (moved from July 24 on 11/7/24) | C
5 implementation support packages initiated to address agreed priority areas | 30 Sep 24 | C
Programme of shared learning in place, connecting practitioners and commissioners to implementation best practice | 30 Nov 24 | G
Developed and tested impactful approaches for involving people and communities in developments in all new prioritised guidance | 31 Mar 25 | G
RAG rating key: C= complete; G= green; A= amber; R= red
All figures as of 31 Oct 2024 unless otherwise stated
Notes on RAG status:
Baseline being established for 24/25 which will be available in March 2025.
We have reduced the number of implementation support packages to be delivered in 24/25 from 5 to 3, to ensure high quality resources are delivered in the capacity available.
1
1
2
2
2

## Slide 14: Brilliant Organisation: Exception report
RAG rating:
Amber
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
Communications
LinkedIn continues to outperform other social channels in terms of engagement and follower growth (+2,8k). The statins data story was the most successful piece of content in October with a 14.5% engagement rate (baseline is 5%).
Phase 1 of the brand marketing campaign saw a significant increase in traffic (326%) to committee recruitment web page.
DIT
Office move (IT set up, desk assembly) as priority focus within initial soft user testing and ‘usual’ usage of the new office opening on 2nd December
Communications on DDAT Single front door completed to provide user transparency on prioritisation of requests for support
People
Business Partnering work has commenced with external OD support to roll out the model
Restorative Just Learning being delivered to key forums to spread the ethos and learning of approach
Leadership development in Healthtech, Medicines and Guidelines
Finance
2024/25 Pay awards and arrears processed in October and November.
New forecasting tool developed to help speed up process and reporting timelines. Planned period of dual running in Q4 ahead of full implementation in 2025/26.
Key activities for next month
Communications
Tirzeptide guidance has a clear and comprehensive comms plan, co-ordinated and aligned with key system partners and associated engagement activity led by Implementation and Partnerships
Over 1,000 people have registered for webinar in Dec on how NICE plans to use and evaluate AI technologies – first activity in wider AI comms plan, working with Science Evidence and Analytics team.
Internal communications channel review findings being put into action starting with changes to the weekly newsletter to staff (YW@N) and the blog process.
DIT
Support for the office opening and decommissioning of City Tower
As per the strategic risk register, preparation for submission of Cyber Essentials certification in December
Finance
Update medium-term financial plan assumptions following October budget statement and latest SR25 intelligence to inform business planning and budget setting for 2025/26.
People
Manging Change Well toolkit being designed by People Team.
Work underway on People Strategy for the next 3 years.
Key issues, risks and mitigants
Very low
Low
Medium
High
Very high
Workstream | Risk | I | L | S | Key Controls
Finance | There is a risk we miss our KPI target to end the year with a surplus of less than £1m.​ | 2​ | 4​ | 8​ | Options to utilise the underspend have been explored at ET. There is a focus on expenditure that will help achieve current objectives for 24/25, rather than create new objectives (due to capacity constraints).
DIT | Cyber security (as per strategic risks) | 5 | 4 | 20 | Cyber activities are being progressed and reported to ARAC. Risk is being tracked in the Strategic Risk Register.
Communications | Narrative explaining final tirzepatide guidance to stakeholders and public is not coordinated across the health system or aligned with system partners | 3 | 3 | 9 | A clear and comprehensive comms plan, and associated engagement activity are co-ordinated and aligned with key system partners

## Slide 15: Brilliant organisation: High-level summary of performance
NICE Business plan KPIs | Actual YTD | KPI Performance target 24-25 | KPI starting Performance 23-24 | % Increase vs 23-24
Media coverage of NICE that is positive in sentiment | 79% | 80% | 80% | 1-percentage points (pp)
Media coverage that is generated by NICE includes at least one NICE key message | 55% | 60% | 54% | 1+ pp
Representation of ethnic minority, disabled and LGBTQ+ colleagues at all levels | Ethnic 19.7% Disabled 10% LGBTQ+ 8.4% | Ethnic 20.3% Disabled 10.44% LGBTQ+ 9.17% | Ethnic 18.21​% Disabled​ 9.49% LGBTQ+​ 8.34% | +1.49pp +0.51pp +0.06pp
Number of informal resolutions | 33 | 31 (50% increase) | 21 | +57%
Financial position (current forecast assumption) | Full-year forecast outturn £1.38m underspend | No deficit, Surplus <£1m | No deficit, Surplus <£1m (Achieved) | 
NICE Bus Plan Milestones | Due Date | RAG
Launched a new Equality, Diversity and Inclusion Roadmap including new objectives to improve staff experience and representation | Q1 | C
Rolled out Power-BI enabled detailed financial forecasting and scenario planning to increase accuracy of forecasts and engage operational teams | Q3 | G
Fully embedded finance business partnering to improve financial input into directorate decisions | Q4 | G
Completed a successful office move to our new Manchester office | Q3 | A
Notes on RAG status:
This KPI is volatile and is dependent on how much of our spokespeople's quotes the media choose to use. Message uptake was lower on the launch of the tirzepatide funding variation consultation.
Although slightly below target, gradual improvements are being made against the 23/24 starting performance.
The KPI is amber due to a strong performance for TA/HST cost recovery and a higher than planned vacancy rate, meaning NICE is forecast to underspend by £1.4m against plan.
1
RAG rating key: C= complete; G= green; A= amber; R= red
All figures as of 31 Oct 2024 unless otherwise stated
1
2
2
3
3

## Slide 16: Financial performance as at 31 October 2024
Update since month 6
The year-to-date underspend decreased to £1.9m during October. This was a reduction of £0.7m due to the impact of the 2024/25 pay award (5.5%) being processed in October. The additional impact of changes to pay progression increment steps will impact the November position.
Although the budget only planned for a 2% award, several directorates were able to absorb the impact of the increased uplift due to savings from vacancies. However, some directorates are now showing an overspend as a result of the pay award pressure. This impact will be reviewed and budget will be transferred from reserves once the DHSC provide additional funding for the impact (expected in January).
The current forecast underspend of £1.4m is based on current trends and known potential liabilities. The second table sets out the potential ranges in up/downside scenarios. As shown in the table, DHSC may withhold funding if the underspend materialises, however, if this doesn’t happen (or the other scenarios materialise) there is a risk of a significant underspend.
Full year forecast - scenarios
Spend category | YTD budget £000 | YTD actual £000 | YTD Variance £000 | Annual budget £000 | Estimated outturn £000 | Forecast variance £000 | Commentary
Pay | 35,597 | 35,088 | (509) | 61,205 | 60,883 | (322) | The 2024/25 pay award (5.5%) increase and arrears were paid in October.
Non-Pay | 13,476 | 13,227 | (249) | 25,272 | 27,337 | 2,265 | Forecast overspend is driven by potential costs of office move and dilapidation costs
Income | (15,763) | (16,963) | (1,200) | (27,135) | (28,605) | (1,470) | Forecast surplus income is due to TA/HST cost recovery being above plan.
Total – baseline* | 33,310 | 31,352 | (1,958) | 59,342 | 59,614 | 272 | Baseline overcommitment (before adding additional funding)
TBC: Funding adjustment |  |  |  | 1,650 | 0 | (1,650) | Budget transfer expected to contribute to cost of 24/25 pay award.
Total - adjusted baseline | 33,310 | 31,352 | (1,958) | 60,992 | 59,614 | (1,377) | Forecast underspend
Uncertainties / Opportunities | Worst-case FOT (£000) | Best-case FOT (£000) | Comments
Current forecast assumption | (1,377) | (1,377) | Current assumed underspend (per table above)
Office move costs & liabilities | - | (1,000) | Forecast outturn assumes £2m costs associated with the office move, although this is subject to negotiation.
TA-HST programme income | 300 | (600) | Forecast assumes the most-likely income is £13.7m income, but possible range is between £13.4m and £14.3m.
Tech Debt / Contingent Labour | 100 | (250) | Tech Debt cost brought forward from planned 25/26. Contingent labour to cover sickness and gaps in staffing. Best-case assumed slippage on forecast spend.
Timeliness Programme | 150 | (250) | Forecast assumes £0.8m of the £1.2m budget will be utilised, but the team are looking for options to utilise some of this underspend.
Funding adjustment | 827 | - | DHSC has indicated some funding may be withheld in Q4 if the forecast underspend materialises. This would reduce our net spend to (or near to) breakeven.
Deficit / (Surplus) - Range | 0 | (3,477) | 
*Note: Previous months baseline budget included data for depreciation charges against capital assets and leases (approximately £2m budget and £1.4m expenditure). This data has been excluded this month as the budget is ringfenced for those costs and the underspend cannot be utilised for other operating expenses and opportunities.

## Slide 17: Appendix to Brilliant organisation
 | YTD | Target | RAG
Sickness rate - overall | 3.05% | 3% | G
Total turnover rate | 13.5% | N/A | N/A
Voluntary turnover | 7.97% | N/A | N/A
Non voluntary turnover | 5.53% | N/A | N/A
Complaints | 100% of complaints responded to within 20 working days | 80% of complaints acknowledged and responded to within 20 working days | G
All figures as of 31 Oct 2024 unless otherwise stated
People
Communications
 | YTD | Target | RAG
FOIs | 100% | 90% of FOIs responded to with 20 working days | G
Parliamentary questions | 89% | 90% of Parliamentary Questions responded to within the requested time frame | A
Newsletter subscribers | 64,742 | 69,771 (this target represents a 10% increase on last year's subscriber total) | A
Social media followers – new WhatsApp channel | 6.5k (launched 22/07) | 5k followers on Whatsapp since 22 July surpassing our KPI of 2k after 6 months | G
RAG rating key: C= complete; G= green; A= amber; R= Red

## Slide 18: Appendix to Brilliant organisation
All figures as of 31 Nov 2024 unless otherwise stated
DIT
RAG rating key: C= complete; G= green; A= amber; R= Red
Commentary:
Some infrastructure services moved to London or temporary Manchester during office move to ensure user experience not impacted.
2 NHSE Critical/high cyber alerts investigated during November. One not applicable to NICE, one resolved with vendor recommended actions.
November staff phishing campaign ongoing – compromise rate of 24% predicted but reporting 0% as not calculated until campaign closes
Phase 1 of cyber transformation programme, focus on prevention and governance on track as reported to ARAC.
P2 incidents across a range of services. All resolved or work arounds in place pending root cause resolution

## Slide 19: Headline description of key projects to deliver NICE aims
NICE aim | Project name | Project headline description
Timely and High-Quality Guidance | Rules Based Pathway (RBP) | Establishing the rules and principles on which NICE and NHS England will work in partnership to evaluate, commission and fund medical technologies
 | Improving Timeliness and Staff experience (ITSE) | Improved timeliness by standardising and improving processes across guidance producing centres, through the use of digital tools and continuous improvement approaches
 | Incorporation of TAs into guidelines | Inclusion of medicines and HealthTech recommendations within guidelines to make NICE guidance more useful and useable
Useable | Content governance and structured recommendations | Organisations that produce digital content need a process to ensure their content is produced efficiently, and is consistent, of high-quality and accurate. This is content governance. We will create a governance framework that outlines how committee recommendations are converted into guidance products that are centred around user needs and agreed house style. Create more actionable, structured recommendations across different types of guidance to benefit users.
 | Knowledge platform | Procure and implement knowledge platform which structured content will be migrated to.
Impactful | Measurement uptake | Measure uptake of our guidance and use that data to ensure NICE focuses on our priorities.
 | Amplify priority partnerships | Work closely with critical stakeholders who can amplify our guidance in priority areas to help get the best care to patients fast.
 | Targeted implementation support | We will use implementation science to focus on system priorities populations with identified health in equalities and other areas that matter most to people and communities.
 | Public involvement best practice approach | Implementing a new way to reach the right members of the public at the right time in the right way to increase uptake of guidance and support getting the best care to people fast.
 | Implementation support toolkits | Development of comprehensive implementation support toolkits where implementation challenges already exist or are anticipated