## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
24/05 | 2024-05-15 | 7 | Board to hold a session on NICE’s commercial strategy once this has been further developed | PT/AW | 2025-09-01 | This will be discussed at the September Board seminar. | Open | n/a
24/19 | 2024-12-11 | 10 | Board to be briefed on the implications for NICE of the outcomes of the review of patient safety across the health and care landscape. | JB | 2025-07-01 | Briefing emailed to the Board for information. | Closed | 2025-07-22
25/01 | 2025-03-19 | 6 | Advise the Board of whether any amendments to the prioritisation board's forward view or the prioritisation criteria were required following the publication of the 10 Year Health Plan. | JB | 2025-07-01 | An initial review of the NICE Prioritisation Board's decision-making criteria has been completed, noting the "three shifts" in the NHS 10-year plan and specific requirements for NICE. No update to the prioritisation criteria is required at this time. The next iteration of the Forward View is due to publish in October. We are currently working with a full range of stakeholders to identify the key priorities for NICE in light of the 10-year plan and our strategic direction. These will be considered in detail by the Prioritisation Board, and the Forward View will be revised substantially, in both presentation and content, as a result. | Closed | 2025-07-22
25/02 | 2025-03-19 | 6 | Board to be updated on progress with the HEMA project with ICER and CADTH. | NC | 2026-03-01 | Written update circulated in May 2025 and a short paper on the first project will be provided in March 2026. | Open | n/a
25/03 | 2025-03-19 | 8 | Further work to be undertaken on the strategy for improving the uptake and adoption of NICE guidance to identify (a) the actions that will be undertaken more widely across the priority areas; and (b) the targeted actions that will have greatest impact on a small number of NICE recommendations within these wider priority areas. | CM | 2025-06-01 | The Board actions for priority areas and measurement approach will be agreed with the usable and Impactful oversight group in July 2025. | Closed | 2025-07-22
25/04 | 2025-05-20 | 6 | Board to be updated on the work with the MHRA to enable guidance to publish earlier and on the discussions with the life sciences industry on how to increase the proportion of optimal topics. | HK | 2025-07-01 | This is being addressed as part of the update on the 10YP, life sciences sector plan and VPAG renegotiation | Closed | 2025-07-22
25/06 | 2025-05-20 | 6 | Board to be updated on the outcome of the recovery testing. | RV | 2026-03-01 | A plan for business continuity testing and recovery is in place that will run across the financial year. Periodic progress updates will be provided to the Audit and Risk Assurance Committee (ARAC). | Closed | 2025-07-22
25/07 | 2025-05-20 | 7 | Board to be updated on any required changes to the business plan following the publication of the 10 Year Health Plan and other government reviews. | SR | 2025-07-01 | Proposed changes presented to the July public Board meeting. | Closed | 2025-07-22
25/08 | 2025-05-20 | 8 | Risk around the fidelity of content to be added to the risk register for the knowledge platform. | CM | 2025-06-01 | Complete | Closed | 2025-07-22
25/09 | 2025-05-20 | 10 | Board to be updated on the monitoring of the frequency of health inequality considerations and how these are handled by the committees | HK | 2026-07-01 | SP&R are currently working on health inequality (HI) implementation activities, e.g. training for technical teams, external assessment groups and committees. We are also tracking the HI considerations by committees following the modular update. We propose to update the Board in July 2026, to give time for a suitable number of topics to be considered by the committee after the publication of the HI modular update. | Open | n/a
25/10 | 2025-05-20 | 11 | Audit and Risk Assurance Committee to review the outcome of the recovery testing and report their findings to the Board. | RV / AL | 2025-09-01 | ARAC to be briefed once testing has taken place. | Open | n/a