## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
24/05 | 2024-05-15 | 7 | Board to hold a session on NICE’s commercial strategy once this has been further developed | PT/AW | 2025-09-01 | This will be discussed at the September Board seminar. | Open | n/a
24/19 | 2024-12-11 | 10 | Board to be briefed on the implications for NICE of the outcomes of the review of patient safety across the health and care landscape. | JB | TBC | Awaiting publication of the review of patient safety across the health and care landscape led by Dr Penny Dash. | Open | n/a
25/01 | 2025-03-19 | 6 | Advise the Board of whether any amendments to the prioritisation board's forward view or the prioritisation criteria were required following the publication of the 10 Year Health Plan. | JB | 2025-07-01 | Action open while we await publication of the 10 Year Health Plan. | Open | n/a
25/02 | 2025-03-19 | 6 | Board to be updated on progress with the HEMA project with ICER and CADTH. | NC | 2026-03-01 | Written update to be circulated in May 2025 and short paper on the first project will be provided in March 2026. | Open | n/a
25/03 | 2025-03-19 | 8 | Further work to be undertaken on the strategy for improving the uptake and adoption of NICE guidance to identify (a) the actions that will be undertaken more widely across the priority areas; and (b) the targeted actions that will have greatest impact on a small number of NICE recommendations within these wider priority areas. | CM | 2025-06-01 | We are working with internal and external stakeholders to refine the approach to the measurement of the impact of NICE guidance, developing a range of measures that reflects both the routine work to support adoption of the whole NICE guidance portfolio, as well as targeted actions/measures in a small number of areas that will have the most impact for our users and for taxpayers. An update will be provided to the Executive Team and Board by June 2025. | Open | n/a