## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
25/09 | 2025-05-20 | 10 | Board to be updated on the monitoring of the frequency of health inequality considerations and how these are handled by the committees | HK | 2026-07-01 | SP&R are currently working on health inequality (HI) implementation activities, e.g. training for technical teams, external assessment groups and committees. We are also tracking the HI considerations by committees following the modular update. We propose to update the Board in July 2026, to give time for a suitable number of topics to be considered by the committee after the publication of the HI modular update. | Open | n/a
25/13 | 2025-09-18 | 5 | NICE Advice team to present to a future Board Seminar on their activities, including their success in adopting a more commercial mindset. | TS | TBC | To be covered as part of a wider discussion of the commercial income strategy with the Board in the next financial year. Timing TBC. | Open | n/a
25/23 | 2025-12-10 | 11 | Board to hold a follow-up discussion looking more broadly at NICE’s role in patient safety in the health and care system. This should also discuss the arrangements for updating NICE guidance following a safety alert and the level of risk arising from any time-lag in updating NICE guidance following such alerts. | JB | 2026-05-01 | Follow-up discussion scheduled for May board seminar. | Closed | 2026-05-19
25/26 | 2025-12-10 | 12 | Next annual equality report to include information on the diversity of the lay members | HW/CM | 2026-09-01 | To be included in the next report. | Open | n/a
26/01 | 2026-03-18 | 7 | Data breach reporting to distinguish between breaches caused by NICE and those attributable to third parties. Consideration to be given as to whether the future target should reflect any year-on-year variation in activity volumes, rather than using the absolute number of breaches as the measure. | HK / TS | 2026-05-01 | The KPI for 2026/27 has been updated to only include breaches caused by NICE and where NICE was aware the data was confidential. The target has been set as an absolute number as calculating the breaches as a percentage of the volume of confidential information processed by NICE would be highly manual and therefore unduly time consuming. | Closed | 2026-05-19
26/02 | 2026-03-18 | 7 | Board to discuss the analysis of the factors behind the increase in the proportion of innovation scorecard medicines showing improved use in order to identify any lessons learnt. Board to also discuss the analysis of the underpinning sub-measures, to understand where there has been increased uptake of medicines and any variation. | CM | 2026-07-01 | Update will be provided to the Board in July when year-end data is available. | Open | n/a
26/03 | 2026-03-18 | 7 | Board to receive an update on the work to review the mandatory training targets and strengthen the escalation processes in the event of non-compliance. | HW | 2026-05-01 | Following engagement and discussion, NICE has simplified its mandatory training framework to reduce burden and strengthen compliance. Three high risk modules (Cyber, Fraud and Information Governance) will carry a 95% target, with all other mandatory training set at 90%, improving clarity and alignment with comparable organisations. A revised escalation framework will go live by end June 2026, shifting from a module by module approach to stronger individual and managerial accountability in line with our cultural direction. The People team will support implementation through webinars teaching colleagues how to view and own their data at individual and managerial levels and a clear reporting cadence to enable ownership of compliance data. | Closed | 2026-05-19
`