## Slide 1: 2024/25 Integrated Performance Report (IPR)
May 2025

## Slide 2: Contents
Section | Slide number | Lead
Executive summary – highlights and challenges | 3 | All ET
Summary of performance – Relevance | 4-5 | Jonathan Benger
Summary of performance – Timely and high quality | 6-9 | Sam Roberts
Summary of performance – Usable | 10-11 | Clare Morgan
Summary of performance – Impactful | 12-13 | Clare Morgan
Summary of performance – Organisational Brilliance | 14-16 | Helen Williams
Financial Performance | 17 | Pete Thomas
Digital, Data and Technology (DDAT) Report | 18 | Raghunath Vydyanath
Appendix A: Headline description of key projects | 19 | N/A - appendix
Appendix B: Description of optimal and divergent topics | 20 | N/A - appendix

## Slide 3: Executive summary of NICE Business Plan progress
3
Area | Status | Key highlights and successes (March 2025) | Key challenges
Focusing on What is Most Relevant | Green | Published the revised Highly Specialised Technology (HST) routing decision criteria Prioritised 20 from 27 topics (74%) that aligned with the wider NHS and social care priorities Published our second annual Forward view Ongoing positive safety team engagement with the MHRA on a range of topics to support issues relating to Regulation 28 coroner reports, Drug Safety Updates and reciprocal exchange placement between safety teams. | Number and complexity of clarifications sought following prioritisation decisions, particularly Highly Specialised Technology routing decisions.
Providing High Quality & Timely Advice | Green | Timeliness: Improvement in timeliness of medicines evaluation: 26% reduction in average time from marketing authorisation to NICE recommendation Methods: Health inequalities modular update revised following consultation. Final HTA Lab dementia report finalised and published. Severity modifier is working as intended. Incorporation of Technology Appraisals (TAs): 35% TA incorporations (183 out of 520) by the end of March 24, exceeding target of 170. Significant stakeholder and board engagement. Rules Based Pathway: Progress on manual to apply funding requirement to HealthTech guidance. Documented pathway and commercial framework in development Late-stage assessment: Our 8 pilots have shown that assessing HealthTech products already in widespread use is valuable to NHS decision-makers. We found that evidence to differentiate between products, and to justify price variations between them, is not always readily available. We will conduct after action reviews with stakeholders to capture learnings from the pilots before consulting on final methods and processes for the programme. | Timeliness: Challenges with staff capacity to test and scale change ideas. Methods: Continuing to monitor the feedback from the severity modifier. Incorporation of TAs: Teams continue to face capacity challenges as work intensifies and complexity of incorporation topics increases. Progress work looking at out we handle newly published TAs. Rules Based pathway: Requires alignment with the 10 Year Health plan and spending review so may need to adapt approach when those policies conclude.
Ensuring our Advice is Usable | Green | Content: NICE Digital Team has updated the existing Publishing system to enable publication of Structured Recommendations in guidance; planning started for User Testing of publishing Structured Recommendations for guidelines; started work within Timeliness Programme to consider improvements to content creation – a focus for 2025/26. Product: User research findings shared on the way users interact with incorporated Technology Appraisals (TAs) within guidelines; established metrics for measuring NICE website search performance; reported on the research findings describing the “top tasks” that users come to NICE's website for. Knowledge Platform: Further co-development of the data model from the Amazon Web Services Proof of Concept, with content modelling and user interface demonstrated Corporate Website Content- Continued work on in-page navigation, with most corporate website pages expected to migrate by Q2 2025/26, including navigation to the Guidance section. | Knowledge platform: To agree the next steps and develop business case for delivery and implementation of a solution to meet the business needs for content creation, management and publication based upon recommendations and learnings from the proof of concept, within the timelines required for the May NICE Board.
Demonstrable impact | Green | Uptake Measurement and System Intelligence.Established new processes for routine updates on health and care system intelligence for NICE decision makers, with more detailed analysis provided in priority areas. Implementation Support: Draft strategy to improve the uptake and adoption of NICE guidance approved by Board. Dashboards developed showing traffic and usage stats for published obesity/tirzepetide resources and the antenatal toolkit. Second tirzepetide support tool (practical prescribing guide) published. Developing the suite of next implementation tools and resources supported by Voluntary Scheme for Branded Medicine Pricing, Access and Growth (VPAG) funding. Prepared the Health Inequalities update for the May Board. Public Involvement Best Practice Approach: Progressing several Continuous Quality Improvement (CQI) projects to understand and improve the experience of public (including carers) involvement in NICE committees. | Implementation of the adoption and uptake strategy, aligning team activities and capacity to the strategy. Uncertainty about the future role of Integrated Care Boards (ICBs) and NHS England are affecting partner organisations capacity to work on joint projects.
Brilliant organisation | Amber –underspend​ exceeds target | People: People strategy event and first session of Restorative Conversations held. Delivery of bullying and harassment recommendations has started; Active Bystander Commission is now live Continuous Quality Improvement (CQI): 60% of 25/26 Business Plan projects have stated intention to use CQI Comms: 528 delegates attended a lively and engaging NICE Conference on 27 March, readout on the event evaluation is very positive. Thought leadership messaging about the vision for our HealthTech programme proactively placed in 14 trade publications. Technology: 100% compliance with service availability targets, Responses to NHS critical cyber alerting within expected timescales. Finance: Completion of 2024/25 financial year. | Full year underspend exceeds our KPI. Capacity constraints and spend controls has meant that we have been unable to fully utilise the underspend arising from vacancies and increased income. Adapting to new ways of working within the People Team due to current changes for agility. Addressed through consistent, clear and open communication channels and need for colleagues to step up in respective spaces. Limited capacity to support teams applying CQI. To be addressed through the ‘embedding improvement’ project.
3

## Slide 4: Relevance: Exception report (March 2025)
RAG rating:
Green
Key highlights / what’s been achieved and headline progress against outcomes and KPIs
We have published the revised Highly Specialised Technology (HST) criteria.
We have published the interim Forward view for 2025/26.
We have responded to recommendations following the Government Internal Audit Agency (GIAA) audit – this has been very positive overall.
Held a very successful reflection, planning and improvement session for the Prioritisation Board.
Key next steps
We will review the terms of reference and membership of the Prioritisation Board.
Develop an improvement plan to address the recommendations from the GIAA audit and track the progress of improvements we have put in place during 2025-26.
Progress key internal actions required in response to patient safety issues raised by Regulation 28 reports, Drug Safety Updates and other sources, including Domestic Homicide Reviews.
Operationalise an exchange placement between safety teams with Medicines and Healthcare products Regulatory Agency (MHRA), expected to begin in June 25.
Key risks and mitigants
Risk | I | L | S | Key Controls
Some developer teams could reach their capacity and be unable to take new topics from Prioritisation Board (PB). | 3 | 4 | 12 | Developing ways to explore relative priority of topics considered by the Prioritisation Board - looking at potentially using the voting scores to determine relative priority, but it may also be a matter of re-presenting prioritised topics to the Prioritisation Board and then asking them to undertake a relative prioritisation exercise.
The Prioritisation Board could reach its capacity to work through and consider the volume of topic suggestions put forward. | 3 | 3 | 9 | Refining implementation of stage 1 process to improve efficiency and sustainability as we learn more now the ‘suggest a topic’ function is in use. We have refined the process by embedding a review by Consultant Clinical Advisors before Prioritisation Board. They review the stage one briefings and the proposed prioritisation decision; PB then reviews those decisions.
Volume and complexity of clarification requests impacts on Surveillance team capacity. | 3 | 3 | 9 | Engaging with Medicines evaluation team colleagues to develop a processes for effectively responding to clarification requests.
Very low
Low
Medium
High
Very high

## Slide 5: Relevance: High-level summary of performance
Indicator | 24-25 Actual | KPI performance target 24-25 | KPI starting performance 23-24 | Trajectory
% of positive decisions made by the Prioritisation Board that align to key NHS and social care priorities, including those described in our annual Forward View | 74% | 90% | Not applicable (N/A) – new measure | N/A – new measure from Oct 24
% of responses to Regulation 28 reports, Health Services Safety Investigation Body (HSSIB) safety recommendations and safety alerts within specified and/or statutory timeframes | 100% | 95% | 90-95% | 
Business Plan Milestones | Due Date | RAG
Common prioritisation framework published following public consultation and agreement with system partners | Q1 | C
NICE’s Prioritisation Board launched | Q1 | C
Prioritisation Board’s forward look published | Q1 | C
Single horizon scanning function operational, linking with external providers | Q2 | C
Agreed an approach for recognising guidance from other organisations in areas where NICE does not produce guidance | Q2 | C
Consulted on any identified changes to routing criteria for Highly Specialised Technology Appraisals | Q4 | C
RAG rating key: C= complete; G= green; A= amber; R= red
Notes on RAG status:
1
27 positive decisions in total; 20 aligned with NHS and social care priorities including those described in forward view. This reflects the first year of Prioritisation Board operation, and will inform the current review of Prioritisation Board processes and activity as well as future forward view publications.
2
2
Responded to 1 Regulation 28 report in March within timelines. We are working on responses to two further reports received in March, however the responses are not due until April and May.
All figures as of 28 February 2025 unless otherwise stated
1

## Slide 6: Timely & High-Quality: Exception report (March 2025)
RAG rating:
Green
Key highlights / what’s been achieved and headline progress against outcomes and KPIs
Timeliness:
All guidance producing teams are now using MS Project to manage their timelines
Each service team has held ‘Plan-Do-Study-Act’ (PDSA) cycles and agreed priorities for next phase
Learning sessions and kick off workshops held to drive improved timeliness of Guidance Development
Methods
Health inequalities modular update has been revised following consultation and taken to Guidance Executive (GE)
Final HTA Lab dementia report published with recommendations for further work on infrastructure costs
Severity modifier working as intended.
Incorporation of Technology Appraisals (TAs):
183 TA incorporations published by the end of March 25, exceeding target of 170
Rules Based Pathways (RBP)
Shortlist of topics for RBP developed
Lifecycle approach including fast followers developed
Commercial approach being explored with case studies
Key next steps
Timeliness:
Undertake programme level process mapping and data collection to baseline ‘as is’ with processes
Work with guidance producing teams to plan focus areas and timelines for 25/26 Improving Timeliness and Content Creation service. Work will be planned in 90-day sprints to scale improvement work up rapidly.
Planning 4-6 weekly virtual learning sessions with teams.
Methods:
Publish health inequalities modular update
Initiate NICE Listens project on severity: started in May 2025; expected to read out by end of Dec 2025
Plan for selected modular updates (EQ-5D-5L value set and surrogate endpoints)
Incorporation of TAs
Develop hypotheses of user behaviour driven by TA incorporation and develop further metrics
Rules Based Pathways
Final legal checks on operationalising Rules Based Pathway
Finalise topic selection approach and criteria
Finalise commercial approach
Key risks and mitigants
Workstream | Risk | I | L | S | Key Controls
Improving timeliness | Approach to the next phase of the timeliness programme (guidance production) might perpetuate siloed working and decrease standardisation | 4 | 4 | 16 | Incorporate subject matter experts from different directorates at key stages to ensure alignment and use formal communication channels to promote scale and spread of approach.
 | Limited resources availability could reduce the effectiveness of PDSA and lead to missed opportunities for learning and improvement | 5 | 3 | 15 | Develop detailed project resource plan to inform project schedule. Identify ‘quick wins’ that could free up team members time which could be reinvested
Rules Based Pathway | Funding may not be available for NICE approved technologies | 4 | 4 | 16 | RBP project will explore potential funding routes for approved technologies.
Methods | NICE’s decision around the severity modifier is not universally understood and may be challenged by stakeholders | 3 | 4 | 12 | Monitor use of the severity modifier. Engagement on industry-funded societal preference work. Launch NICE Listens severity weighting project
Very low
Low
Medium
High
Very high
6

## Slide 7: Timely & High-Quality: High-level summary of performance (1 of 3) (March 2025)
Indicator | 24-25 Actual | 24-25 Target | 23-24 starting performance | Change from 23-24 performance
Medicines - Mean time between marketing authorisation and NICE recommendation (optimal and divergent)* | 335 calendar days (N=53) | Improvement on 23-24 baseline | 452 calendar days | 26% Improvement
Medicines - Median time between marketing authorisation and NICE recommendation (optimal and divergent)* | 328 calendar days (N=53) | Improvement on 23-24 baseline | 322 calendar days | 2% Slower
Medicines - Mean time between marketing authorisation and NICE recommendation (optimal)* | 48 calendar days (N=11) | 90 calendar days | 36 calendar days | Within target, but 33% above 23/24 mean
Medicines - Median time between marketing authorisation and NICE recommendation (optimal)* | 44 calendar days (N=11) | 90 calendar days | 43 calendar days | Within target, but 2% above 23/24 mean
Business Plan Milestones | Date | RAG
Start routinely incorporating relevant medicine technology appraisals in guidelines | Q1 | C
Understood baseline and opportunities for improvement in guidance producing processes | Q2 | C
Rolled out digital tools that support planning and identified future planning/scheduling needs | Q3 | C
Aligned and digitised some key steps in guidance producing processes | Q4 | C
Reviewed the use of the severity modifier in medicines evaluation and identified remedial actions if needed | Q2 | C
Updated methods for assessing health inequalities in guidance production | Q4 | C
Expanded HTA Lab capacity in line with new VPAG funding and delivered insightful outputs supporting high quality guidance | Q4 | C
Launched 8 Late-Stage Assessment topics | Q4 | C
Consulted (with NHS England) on a medtech rules-based pathway | Q1 | C
RAG rating key: C= complete; G= green; A= amber; R= red
All figures as of 31 March 2025 unless otherwise stated
*Definition of optimal and divergent topics included on slide 21

## Slide 8: Timely & High-Quality: High-level summary of performance (2 of 3) (March 2025)
Indicator | 24-25 Actual | 24-25 Target | 23-24 starting performance | Change since 23-24 performance
Medicines - Mean time between marketing authorisation and NICE recommendation (divergent)* | 410 calendar days (N=42) | Improvement on baseline 23-24 | 540 days | 24% improvement
Medicines - Median time between marketing authorisation and NICE recommendation (divergent)* | 413 calendar days (N=42) | Improvement on baseline 23-24 | 365 days | 13% slower
Medicines - Percentage of optimal topics published in 2024/25 (year to date) | 21% (N=11) | Improvement on 23-24 baseline | 17.5% | +3.5 percentage point improvement
HealthTech - Mean time to publish HealthTech guidance | 437 calendar days (N=28) | Improvement on 23-24 baseline | 490 days | 11% improvement
HealthTech - Median time to publish HealthTech guidance | 400 calendar days (N=28) | Improvement on 23-24 baseline | 402 Days | 0.5% improvement
Centre for Guidelines (CfG) – % of quality standard updates published alongside guideline updates | 100% (N = 7) | 30% | N/A | N/A
% of Technology Appraisals (TAs) retrospectively incorporated into guidelines by end of 24/25 | 35% (N=183) | 33% (170 out of 520) | N/A | N/A
All figures as of 31 March 2025 unless otherwise stated

## Slide 9: Timely & High-Quality: High-level summary of performance (3 of 3) (March 2025)
Timeliness summary (mean days)
Timeliness summary (median days)
We have seen a slight increase in the overall median (driven by divergent appraisal topics). A significant proportion of our appraisals are getting faster. We have published more appraisals within 90 days of the Marketing Authorisation (21% in 24/25 compared to 17.5% in 23/24) and we are now completing more appraisals within the designed 240 working day process timeframe (44% in 24/25). We have also reduced the number of outliers which are topics that are regarded to be extremely off process.
We are continuing to explore our data to understand the rationale for the median increase. We are reviewing the start dates of NICE appraisals and if the time frame between the Marketing Authorisation and the start of the NICE process has increased and why. We are also exploring whether those appraisal topics that are taking more than 240 days are taking much longer than 23/24. Both of these factors are expected to be major drivers for the increase in the median in the divergent topics.

## Slide 10: Usable: Exception report (March 2025)
RAG rating:
Amber
Key highlights / what’s been achieved and headline progress against outcomes and KPIs
Content:
NICE Digital Team has updated existing Publishing system to enable publication of Structured Recommendations in guidance.
Continued engagement with Centre for Guidelines to co-design a solution for Structured Recommendations in guidelines.
Planning started for User Testing of publishing Structured Recommendations for guidelines.
Started work within Timeliness Programme to consider improvements to the way we create content – a focus for 2025/26.
Product:
Findings shared internally from the way users interact with incorporated Technology Appraisals (TAs) within guidelines.
Established metrics for measuring NICE website search performance.
Plans for integrated guidance product proposed metrics have been shared internally.
Started to share research findings describing the “top tasks” that users come to NICE's website for.
Knowledge Platform:
Further co-development of the data model from the Amazon Web Services (AWS) Proof of Concept (PoC), with content modelling and user interface demonstrated
Corporate Website Content:
Progress made on in-page navigation.
Most corporate website pages, including navigation to the Guidance section, will migrate by Q2 2025/26.
Key next steps
Content:
Define work required for transformation of content creation
Continue to engage on development of data model being developed through the AWS Proof of Concept to maintain alignment.
Continue to engage with Centre for Guidelines on next steps to co-design a solution for Structured Recommendations in Guidelines.
Product:
Continue to iterate TA incorporation measures, expanding sample size, defining hypotheses, and refining measures.
Gain agreement for integrated guidance product proposed metrics
Work with usable programme colleagues on initial scope and sizing of third-party requirements for secondary content re-use
Knowledge Platform:
Output from AWS Proof of Concept (data model etc) will be completed and moved into NICE’s account, including NICE receiving detailed documentation and handover sessions.
Agree next steps and business case for delivery and implementation of a solution to meet the business needs for content creation, management and publication based upon recommendations and learnings from the proof of concept
Corporate website content:
Continue migration work and steady drumbeat of storytelling content to highlight NICE’s role in health and care.
Key risks and mitigants
Workstream | Risk | I | L | S | Key Controls
Structured Recommendations | If colleagues at all levels across the guidance producing centres are not convinced there is a need for change, then we will be unable to deliver Structured Recommendations | 4 | 3 | 12 | Continue to engage with colleagues to ensure they understand and are bought into the direction and benefits to our users that this work will bring; co-design solutions where possible
Very low
Low
Medium
High
Very high

## Slide 11: Usable: High-level summary of performance
Indicator | 24-25 Actual | 24-25 Target | 23-24 starting performance 23-24
Annual % change in number of users accessing NICE website for guidance and advice | + 3% | Increase on 23-24 | 18.3 million
Annual % change in clicks on guidance products from the NICE corporate website | - 5% | 95,700 (15% Increase on 23-24) | 83,200
Business Plan Milestones | Due Date | RAG
Complete migration to new corporate website | 31 Dec 24 | A
Complete proof of concepts with semantic data model to inform next steps of knowledge platform | 1 July 24 | C
Agree standardised wording and structure for recommendations | 31 Dec 24 | C
Launch a new content governance process for Centre for Health Technology Evaluation (CHTE) and CfG | 31 Dec 24 | A
RAG rating key: C= complete; G= green; A= amber; R= red
Notes on RAG status:
There has been an 5% annual decrease in clicks on guidance products from the NICE corporate website. This reflects the work that has been done to audit and remove old content from the corporate site which has had an impact on clicks through to guidance, however this has improved search engine optimisation which will make it easier to find guidance directly both on the NICE website and from Google.
The first target of going live with the new homepage was met. The timeline to finish migration of corporate pages has slipped into Q2 2025/26.
The deliverables from the AWS Proof of Concept were completed in April 2025 have informed the development of a business case for a platform to enable guidance content management and publication
Work has been absorbed into the structured recommendation project and approach approved by the Programme Board.
1
3
2
1
2
3
4
4
All figures as of 31 March 2025 unless otherwise stated

## Slide 12: Impactful: Exception report (March 2025)
RAG rating:
Green
Key highlights / what’s been achieved and headline progress against outcomes and KPIs
Uptake Measurement and System Intelligence​
Developed an ongoing report of uptake to support the obesity and weight management/tirzepetide implementation programme
Completed work to baseline uptake data across measures in all priority guidance areas
Developed estimates of uptake for key medicines to accompany the next innovation scorecard published in April 2025
Delivery of system intelligence reporting now moved into business as usual, including triaging and responding to requests for system intelligence and providing routine reports of actionable intelligence from engagements.
Implementation support​
NICE Board agreed strategy to improve the uptake and adoption of NICE guidance
Produced dashboard to show traffic and usage stats for published obesity/tirzepatide resources and antenatal toolkit.​
Published second obesity medicines support tool (practical prescribing guide)
Public Involvement best practice approach
Three continuous improvement projects focused on people and communities priorities are now in development, they are:
  Understanding and improving the experiences of people who work with us
  Increasing the impact and value of involvement and engagement
  Improving how we involve carers in our work
Key next steps
Uptake measurement and System Intelligence​
Confirming with stakeholder input our priorities for uptake and adoption programme in 2025/26, including focus of our key performance indicator (KPI)
Developing actionable insights for NICE decision makers on latest update of innovation scorecard
​Implementation support
Implementing the agreed work plan for our partnership with the Race Health Observatory.
Implementing a new process across Implementation, Medicines Optimisation, Publishing and Products for producing implementation tools and resources for our primary users
Developing the next VPAG-funded tools and resources.
Planning NICE/ICB regional roundtable events.
Public Involvement best practice approach
Mapping of the key processes for involvement for guidelines, medicines and health tech.
Commencing focused work on implementation/uptake with the Voluntary Community and Social Enterprise (VCSE) network.
Very low
Low
Medium
High
Very high

## Slide 13: Impactful: High-level summary of performance
Indicator | Actual YTD | KPI performance target 24-25 | KPI starting performance 23-24 | Trajectory
Proportion of agreed priority guidance measures showing an improvement in national uptake (health and care system priority areas, populations with identified health inequalities, areas that matter most to people and the communities). | N/A | N/A | Baseline to be established during 24/25 | N/A
All agreed priority areas have targeted implementation support package in place | 3 | 5 | 0 | 
New partnerships (including VCSE organisations) to amplify the impact of NICE guidance in agreed priority areas. | 5 | 5 | 0 | 
Business Plan Milestones | Due Date | RAG
Developed and implemented a fairer payment policy for involvement and engagement activity | 21 June 24 | C
Routine reporting of prioritised uptake measures in place | 31 July 24 | C
Joint plans in place to amplify the impact of NICE guidance through priority partnerships | 30 Sept 24 | C
5 implementation support packages initiated to address agreed priority areas | 30 Sep 24 | C
Programme of shared learning in place, connecting practitioners and commissioners to implementation best practice | 30 Jun 25 | A
Developed and tested impactful approaches for involving people and communities in developments in all new prioritised guidance | 31 Mar 25 | C
RAG rating key: C= complete; G= green; A= amber; R= red
Notes on RAG status:
Baseline being established for 24/25 which will be available end of March 2025.
Reduction in the number of implementation support packages reduced from 5 to 3 and approved by the Programme Board, to ensure high quality resources are delivered with the capacity available.
New milestone due date 30/06/25 therefore will be incorporated into 2025/26 plans, as part of our stakeholder engagement project.
In 24/25 we tested the use of composite digital stories, based on survey data, for the Digital therapy for chronic tic disorders and Tourette syndrome (HTE25) assessment, and have identified different approaches for the upcoming OCD/BDD guideline. This work will continue into 2025/26 as part of our People and communities involvement and engagement strategy.
1
1
2
2
3
All figures as of 31 March 2025 unless otherwise stated
3
4
4

## Slide 14: Brilliant Organisation: Exception report (March 2025)
RAG rating:
Amber
Key highlights / what’s been achieved and headline progress against outcomes and KPIs
Communications
Endometriosis pill media coverage in 31 outlets (potential readership of 74.4 million); high engagement on LinkedIn: 42,937 impressions, 26.6% engagement rate, 916 reactions, 42 comments, and 112 reposts. Above average engagement was also seen on X.
Primary care-focused brand marketing campaign successfully engaged the target audience, driving high landing page views (result 63.5K, target 40K) and ad click through rates (e.g. Google search result 16.4%, target 8%).
Internal: business planning campaign has involved extensive comms, promotion and the coordination of business plan roadshows; positive feedback from the 3 roadshows: 92% for useful/engaging, 87% for feeling informed, 80% for understanding.
People teams
First People Strategy event has taken place.​
First session of Restorative Conversations has taken place across a broad range of colleagues.​
Begin delivering bullying and harassment (B&H) recommendations. Active Bystander Commission is active/live
All Directorates to ensure they have Equality, Diversity and Inclusion (EDI) action plans in place.
Continuous Quality Improvement (CQI):
Clear recognition of role of CQI to tackle complex problems. 25 projects recognised the need to use CQI to deliver their projects and requested support. Plus 8 other projects that could benefit from applying CQI.
Technology: 100% compliance with live service availability targets, Responses to NHS critical cyber alerting are consistently resulting in deployed fixes within 24 hours of notification, well within the expected timescale of 14 days.
Finance: Completion of 2024/25 financial year.
Key next steps
Communications
Review and refresh of core messaging and communications approach
Quarterly audience perception surveys to commence
Communications and People team will collaborate to conduct a survey to evaluate the effectiveness the last 12 months embedding programme has had.
Office Move:
Continue working with NHS Property Services for the lease and soundproofing at the new Manchester office.
Government Property Agency leading on dilapidations and rent review at City Tower.
Finance
A balanced budget has been set for 2025/26 based on indicative funding confirmation from Department of Health and Social Care (DHSC). To reduce the likelihood of an underspend a longlist of projects and additional resource needs is in place to deploy.
Key issues, risks and mitigants
Workstream | Risk | I | L | S | Key Controls
DIT | Cyber security (as per strategic risks) | 5 | 4 | 20 | Cyber activities are being progressed and reported to Audit and Risk Assurance Committee. Risk is being tracked in the Strategic Risk Register. Risk updated to reflect impact of Artificial Intelligence (AI)
Very low
Low
Medium
High
Very high

## Slide 15: Brilliant Organisation: High-level summary of performance
Indicator |  | 24-25 Actual | 24-25 target | 23-24 starting Performance | Change since 23-24 performance
Media coverage of NICE that is positive in sentiment |  | 81% | 80% | 80% | +1 percentage point (pp)
Media coverage that is generated by NICE includes at least one NICE key message |  | 52% | 60% | 54% | -2 pp
Workforce representation: | Ethnic minority staff | 21% | 20.3% | 18.21​% | +2.79 pp
 | Staff with a disability | 11% | 10.44% | 9.49% | +1.51 pp
 | LGBTQ+ staff | 9.1% | 9.17% | 8.34% | +0.76 pp
Number of informal resolutions |  | 56 | 32 (50% increase) | 21 | +166%
Financial position (current forecast assumption) |  | Year-end outturn £2.35m underspend | No deficit, Surplus <£1m | Surplus <£1m | 
Business Plan Milestones | Due Date | RAG
Launched a new Equality, Diversity and Inclusion Roadmap including new objectives to improve staff experience and representation | Q1 | C
Rolled out Power-BI enabled detailed financial forecasting and scenario planning to increase accuracy of forecasts and engage operational teams | Q3 | C
Fully embedded finance business partnering to improve financial input into directorate decisions | Q4 | C
Completed a successful office move to our new Manchester office | Q3 | C
RAG rating key: C= complete; G= green; A= amber; R= red
Notes on RAG status:
This KPI is volatile and is dependent on how much of our spokespeople's quotes the media choose to use.
Although slightly below target, gradual improvements are being made against the 23/24 starting performance.
The KPI on underspend was not met due to a strong performance for TA/HST cost recovery and a higher than planned vacancy rate.
1
1
2
2
3
3
All figures as of 31 March 2025 unless otherwise stated

## Slide 16: Appendix to Brilliant organisation
People
 | 24-25 Actual | 24-25 Target | 23-24 starting performance | Change since 23-24 performance
Sickness rate | 2.85% | 3% | 2.49% | +0.36pp
Total turnover rate | 12.54% | - | 11.61% | +0.93pp
Voluntary turnover | 7.86% | - | N/A – new indicator | 
Non voluntary turnover | 4.68% | - | N/A – new indicator | 
Proportion of complaints acknowledged and responded to within 20 working days | 100% (N=3) | 80% | 100% | No change
Complaints
Communications
 | 24-25 Actual | 24-25 Target | RAG
Freedom of Information Requests (FOIs) | 98% | 90% of FOIs responded to with 20 working days | G
Parliamentary questions | 98% | 90% of Parliamentary Questions responded to within the requested time frame | G
Newsletter subscribers | 66,629 | 69,771 (this target represents a 10% increase on last year's subscriber total) | A
Social media followers – new WhatsApp channel | 8,860 (launched 22/07) | 5k followers on Whatsapp since 22 July surpassing our KPI of 2k after 6 months | G
RAG rating key: C= complete; G= green; A= amber; R= Red

## Slide 17: Financial performance as at 31 March 2025
Spend category​ | Annual budget £000​ | Outturn £000​ | Outturn variance £000​ | Commentary​
Pay​ | 61,875 | 60,669 | (1,206) | Pay underspend (1.9% against budget) driven by vacancies.​
Non-pay​ | 25,046 | 24,843 | (203) | Underspend on the Improving Timeliness programme, partially offset by Manchester office costs (City Tower and 3PP).
Income | (27,040) | (27,984) | (944) | TA-HST cost recovery above plan. Partially offset by NICE Advice deficit of £0.55m.
Total* | 59,881 | 57,528 | (2,353) | 
Year-end position 2024/25
NICE ended the 2024/25 financial year with an underspend of £2.35m (3.9%). As shown in the table above, the main drivers were underspends on pay and the strong income performance of the TA-HST programme. Further underspends were mitigated by not drawing down the final Office for Life Sciences budget transfer (£1.1m).
Update since last Board meeting
At March’s board meeting, the financial position was reported as at the end of January 2025. Since then, the forecast underspend has increased from £1.8m to £2.4m (£0.6m increase), largely driven by uncertainty relating to the timing and level of some costs of the office move (-£0.6m).
A summary of the changes since the last IPR is shown in the table below.
Comparison (£m) | Jan 25 | Mar 25 | Movement | Change
Annual Budget | 59.9 | 59.9 | - | No change
Forecast outturn | 58.1 | 57.5 | (0.6) | 
Forecast variance | (1.8) | (2.4) | (0.6) | £0.6m net increase in forecast underspend
Operating segments
NICE operates 3 reportable operating segments which are included in the annual accounts. The performance of those 3 segments are summarised below:
The in-year NICE Advice deficit means the available reserves has reduced to £1.3m (from £1.8m at the end of 23/24).
2024/25 | NICE £000 | Technology Appraisals & HST £000 | NICE Advice £000 | Total £000
Gross expenditure | 67,245 | 14,862 | 3,404 | 85,512
Income | (11,424) | (13,701) | (2,859) | (27,984)
Net expenditure | 55,821 | 1,161 | 545 | 57,528
*Note: The above financial statement shows our performance against our Non-Ringfenced revenue budget, which is agreed annually with the DHSC. Our Ringfenced revenue spend was £1.3m against a budget of £2m (depreciation charges against capital assets and leases).

## Slide 18: Digital, Data and Technology (DDAT) Live Services
Stability
18
Commentary:
Annual penetration testing completed for NICE infrastructure and reports received, leading to remediation work plans over coming weeks.
NICE is evaluating additional tooling to protect email users from phishing, which will also provide accessible on-going user risk awareness.
NICE responses to NHS critical cyber alerting are consistently resulting in deployed fixes within 24 hours of notification, well within the expected timescale of 14 days.
GovWiFi is now online in both the Manchester and London offices for NICE staff and guests, making connectivity seamless.
P1 service failure related to use of modern security gateway with legacy planning tools (ongoing issue due to compatibility)
Data as at 31 March 2025

## Slide 19: Appendix A: Headline description of key projects to deliver NICE aims
NICE aim | Project name | Project headline description
Timely and High-Quality Guidance | Rules Based Pathway (RBP) | Establishing the rules and principles on which NICE and NHS England will work in partnership to evaluate, commission and fund medical technologies
 | Improving Timeliness and Staff experience (ITSE) | Improved timeliness by standardising and improving processes across guidance producing centres, through the use of digital tools and continuous improvement approaches
 | Incorporation of TAs into guidelines | Inclusion of medicines and HealthTech recommendations within guidelines to make NICE guidance more useful and useable
Usable | Content governance and structured recommendations | Organisations that produce digital content need a process to ensure their content is produced efficiently, and is consistent, of high-quality and accurate. This is content governance. We will create a governance framework that outlines how committee recommendations are converted into guidance products that are centred around user needs and agreed house style. Create more actionable, structured recommendations across different types of guidance to benefit users.
 | Knowledge platform | Procure and implement knowledge platform which structured content will be migrated to.
Impactful | Measurement uptake | Measure uptake of our guidance and use that data to ensure NICE focuses on our priorities.
 | Amplify priority partnerships | Work closely with critical stakeholders who can amplify our guidance in priority areas to help get the best care to patients fast.
 | Targeted implementation support | We will use implementation science to focus on system priorities populations with identified health in equalities and other areas that matter most to people and communities.
 | Public involvement best practice approach | Implementing a new way to reach the right members of the public at the right time in the right way to increase uptake of guidance and support getting the best care to people fast.
 | Implementation support toolkits | Development of comprehensive implementation support toolkits where implementation challenges already exist or are anticipated

## Slide 20: Appendix B: Description of optimal and divergent topics
Our ability to publish final technology appraisal or highly specialised technologies guidance within 90 days of a medicine gaining marketing authorisation (MA) depends on whether it is classified as ‘optimal’ or ‘divergent’.
Does the medicine meet all of the characteristics of an optimal topic?
Yes
Medicine is categorised as optimal
NICE can publish guidance within 90 days of GB MA
No
Medicine is categorised as divergent
NICE cannot publish guidance within 90 days of GB MA due to external factors
We categorise medicines as either optimal or divergent based on whether it is possible to publish final guidance within 90 days of MA.
Characteristics of an ‘optimal’ topic
NICE is notified of topic >16 months ahead of GB marketing authorisation (GB MA).
Company accepts the NICE topic selection or routing decisions.
Company does not negotiate a delayed evidence submission date.
The technical engagement stage is not required.
Additional data is not provided post evidence submission date.
Cost effective ICER presented and agreed at the first committee meeting leading to final draft guidance (consultation not required).
The topic is not delayed/paused due to commercial discussions (pre or post the committee meeting).
No appeal received for the topic or, if appeal received, appeal points are upheld.
There aren’t other external factors that cause delay to the appraisal timelines.