## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
25/02 | 2025-03-19 | 6 | Board to be updated on progress with the HEMA project with ICER and CADTH. | NC | 2026-03-01 | Written update circulated in May 2025 and a short update was provided to the March Board seminar. | Closed | 18/03/206
25/09 | 2025-05-20 | 10 | Board to be updated on the monitoring of the frequency of health inequality considerations and how these are handled by the committees | HK | 2026-07-01 | SP&R are currently working on health inequality (HI) implementation activities, e.g. training for technical teams, external assessment groups and committees. We are also tracking the HI considerations by committees following the modular update. We propose to update the Board in July 2026, to give time for a suitable number of topics to be considered by the committee after the publication of the HI modular update. | Open | n/a
25/13 | 2025-09-18 | 5 | NICE Advice team to present to a future Board Seminar on their activities, including their success in adopting a more commercial mindset. | TS | TBC | To be covered as part of a wider discussion of the commercial income strategy with the Board in the next financial year. Timing TBC. | Open | n/a
25/18 | 2025-09-18 | 11 | Deep-dive of optimised recommendations in the medicines evaluation programme to be undertaken, to include review of the extent of the optimisation and also whether the optimisation was requested by the company or driven by the committee. | HK | 2026-03-01 | Update provided to the Board in March. | Closed | 18/03/206
25/19 | 2025-12-10 | 8 | Further information to be provided to the Board in March on what processes need to change to deliver the Government's commitment to make the UK the third fastest for medicines access in Europe, including those within NICE’s control, and those which are outside of NICE’s remit. | HK | 2026-03-01 | Update provided to the March Board seminar. | Closed | 18/03/206
25/20 | 2025-12-10 | 8 | Failure rate from phishing exercises to be added to the IPR. | RV | 2026-03-01 | This information is reported to the audit and risk assurance committee however external advice has recommended against including this information in the public performance report | Closed | 18/03/206
25/21 | 2025-12-10 | 8 | Board to be updated in March on the exploration of the scope to mitigate the risk of confidentiality breaches in the medicines evaluation programme through digital tools. | HK | 2026-03-01 | Update provided to the March Board seminar. | Closed | 18/03/206
25/22 | 2025-12-10 | 9 | Board to have greater visibility of the prioritisation board’s work and the issues raised in clarification requests. | JB | 2026-03-01 | The prioritisation board will now report to the Board twice a year (scheduled for May and December). | Closed | 18/03/206
25/23 | 2025-12-10 | 11 | Board to hold a follow-up discussion looking more broadly at NICE’s role in patient safety in the health and care system. This should also discuss the arrangements for updating NICE guidance following a safety alert and the level of risk arising from any time-lag in updating NICE guidance following such alerts. | JB | 2026-05-01 | Follow-up discussion scheduled for May board seminar. | Open | n/a
25/24 | 2025-12-10 | 11 | Further consideration to be given to the frequency of the PSOG’s reporting to the Executive Team. Future reporting to the Executive Team and Board to also include information on NICE’s timeliness in updating guidance in response to patient safety alerts. | JB | 2026-05-01 | Reporting frequency to the Guidance Executive and Board will be increased to six-monthly. | Closed | 18/03/206
25/26 | 2025-12-10 | 12 | Next annual equality report to include information on the diversity of the lay members | HW/CM | 2026-09-01 | To be included in the next report. | Open | n/a