## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
23/17 | 2023-09-21 | 6 | Further information to be provided to the Board at a suitable point on the learning from system intelligence in the context of living guidelines, including how often ‘living’ guidelines should be updated and what data is needed to drive these decisions. | JB | 2024-05-01 | This will be discussed in the context of the later agenda item on the new approach to prioritisation and the commitment to update in priority areas within six months of a Prioritisation Board decision. | Closed | 2024-05-15
24/01 | 2024-03-20 | 8 | Proposal for whether to undertake a targeted or more comprehensive update of the NICE Principles to be brought back to the Board, along with an indicative timescale for this work. | NC | 2024-05-01 | We plan to undertake a comprehensive update of the NICE Principles taking account of learning from transformation and environmental sustainability work. We intend to complete the update by the end of business year 2026/27. | Closed | 2024-05-15
24/02 | 2024-03-20 | 10 | Additional text to be added to the NICE charter to reflect NICE’s role in helping improve productivity. | JG | 2024-03-01 | Text added. | Closed | 2024-05-15