## Slide 1: NICE 2025/26 Corporate Business Plan
DRAFT for Board approval
May 2025
1

## Slide 2: Contents
Executive summary
NICE’s purpose
NICE’s delivery in 2024/25
NICE’s business plan for 2025/26
NICE’s budget for 2025/26
NICE strategic risk register

## Slide 3: Executive summary
NICE is continuing to transform, ensuring our guidance is guidance is more timely and easy to use, more relevant, and has greater demonstrable impact, whilst maintaining our rigour, transparency and independence.
We made significant progress against this transformation in 2024/25:
  To ensure our guidance is relevant, we established a new Prioritisation Board to align our guidance with health system needs
  In terms of improving timeliness, our appraisals of medicines are 26% faster and health tech are 11% faster than the previous year.
  In terms of improving useability of our guidance, we incorporated 35% of historic Technology Appraisals into guidelines.
Next year we will continue to transform through eleven priority projects:
  Improving timeliness programme
  Friction free pathway
  Implementing a rules-based pathway for HealthTech
  Improving our approach to funding variations
  Developing a whole lifecycle approach to guidance
  Implementing a platform to enable guidance content management and publication
  Developing a single programme of support for guidance uptake
  Building financial and commercial agility
  Progressing work on our AI statement of intent
  Strengthening NICE’s reputation and influence
  Embedding improvement into our ways of working

## Slide 4: In 25/26, we will deliver our aims by providing high quality, timely advice that is relevant, usable and impactful
Timely and High Quality | Improving timeliness programme | Improve the timeliness of guidance production across guidelines, health tech and medicines whilst maintaining the quality of our guidance
 | Friction free pathway | Identify areas where NICE, the MHRA and NHSE can work more closely to decrease the time between MHRA marketing authorisation and NICE guidance for medicines
Relevant | Rules based pathway | Work with DHSC and NHSE to develop a clear, consistent, standardised and streamlined rules-based approach to HealthTech evaluations and adoption
 | Improve approach to funding variations | Review the current approach for dealing with Funding Variation Requests and consider areas that need to be amended and strengthened, working closely with DHSC/NHSE
 | Whole lifecycle approach | Assess the lifecycle value of innovations and guidelines with the goal of improving population health
 | Progress AI statement of intent | Position NICE as the leading HTA Agency in the evaluation and use of Artificial Intelligence
Usable | Implementation of a platform to enable guidance content management and publication | Implement a new content creation, curation & product publication and syndication service, underpinned by a knowledge platform
Impactful | Single programme of support for guidance uptake | Refresh NICE’s engagement approach in the health and care system, focusing on a small number of priority topics, a focused programme of implementation support, and the most influential partners
Brilliant organisation | Build financial and commercial agility | Enable NICE to adjust to changing priorities through more sustainable funding and income and a more flexible cost base. This includes the development of new contracting approaches, improved financial management practices and a new commercial strategy.
 | Strengthen NICE’s reputation and influence | Broaden our communications approach to cover content beyond individual guidance decisions, increase our focus on external placement of storytelling content, run a year-long brand marketing and content plan, and complete the corporate website migration
 | Embed improvement into our ways of working | Build knowledge and skills in Continuous Quality Improvement through a learning programme and by coaching staff to use it in their work
4

## Slide 5: NICE’s purpose
Our values drive how we deliver our purpose and priorities
We focus on users first
We know what matters to our users.
We make it our mission to fulfil our users’ needs.
We work with partners when needed to deliver greater impact.
We unite as one team with one purpose
We put our collective purpose above all else to succeed together.
We collaborate more to achieve more.
We know what success looks like and make it happen.
We trust each other to make decisions
We value expertise over seniority.
We share the risk; you make the decision.
We welcome and share honest feedback.
We act boldly
We take the initiative and lead by example.
We push the boundaries to enable radical change.
We test fast and learn faster.
We embrace difference
We take action to include diverse perspectives.
We value each other and treat everyone with kindness and respect.
We take a stand if we see unfairness or disrespect.
Notes: How to use this slide:
1. At the start of a meeting:
Discuss and agree which values are most relevant to a) what is being discussed b) how the meeting is conducted.
2. At the end of a meeting:
Chair to ask if the values identified as relevant to the meeting at the start, were demonstrated throughout the meeting.
Consider the conduct of each person in attendance and meeting content.
Celebrate good practice in line with our values. Identify changes you'll implement at the next meeting.
This slide is ideal for use at large directorate and team meetings.

## Slide 6: The health and care system is changing
We’re seeing:
health service pressures
shared decision making
growth in innovation
vast amounts of data.
NICE is transforming too
NICE’s core purpose remains the same: to help practitioners and commissioners get the best care to people fast, while ensuring value for the taxpayer.
But as the NHS transforms to meet future challenges, we need to play our part too.
6
Notes: NICE is embarking on 5-year transformation journey. Our core purpose is to help practitioners and commissioners get the best care to people fast, while delivering value for the taxpayer. As we transform, this will not change.
Nor will our role as a world-leading health technology assessment body, and the only national body to undertake both technology appraisals (appraising individual medicines or devices) and clinical guidelines.
Yet the world is changing - demands on the health service are greater than ever, we're seeing an expanding role of shared decision-making, an exponential growth in innovation, and vast amounts of data. As the NHS transforms to meet future challenges, we must too.

## Slide 7: How we’re transforming
While preserving our core principles of transparency, rigour and independence,
we're focussed on developing guidance that is...
More timely and easy to use
…by providing timely and usable advice.
More relevant
…by focusing on what matters most.
Greater demonstrable impact
...by learning from data and implementation.
Notes: As we transform, we'll adhere to our core principles of independence, rigour and transparency to develop guidance that is:
more timely and easier for health and care practitioners and commissioners to use
more relevant to the challenges across the health and care system, by focussing on what matters most​
and we'll increase our demonstrable impact by learning from data and implementation. ​
​

## Slide 8: To deliver our purpose, we produce high quality advice that is timely, relevant, usable and impactful
Last year, we aligned our activity to deliver those aims and invested in the foundational programmes to go further in the coming years, delivering all our key business plan objectives.
93%
of our 28 business plan milestones delivered
100%
of total forecast guidance delivered and more medicines evaluation activity than ever before
79%
of our core audience agree or strongly agree that NICE is scientific, rigorous and evidence based
“[NICE] is an essential part of the health system. You have to have an organisation like NICE doing what it does. Otherwise, you don't have a health system that people can have confidence in”
Senior Leader, Royal College, 2024 Reputational Research
8

## Slide 9: NICE’s Delivery in 2024/25

## Slide 10: The progress we’ve made
More relevant
Listening more to the people we serve
Our guidance continued to focus on what matters most through a new integrated approach to topic selection and prioritisation.
Looking at new types of innovation
We continued exploring new medicine classes, for example disease modifying drugs for dementia and gene editing therapy.
Evolving our methods for calculating value
The severity modifier is operating as intended. It has been applied more widely than the end of life modifier and is resulting in a higher proportion of positive recommendations.
Methods for accounting for health inequalities are being updated.
More timely and usable
Improvements in appraisal timeliness
26% improvement for medicines.
11% improvement for HealthTech.
Supporting industry
We are transforming our HealthTech programme to increase the amount of health tech the NHS adopts.
Everything in one place
We have incorporated approximately
35% of our historic technology appraisals into current guidelines.
Simplifying our language
We’ve simplified our recommendation types down from 33 to 41 to aid implementation and help our users understand them quickly.
1: Across HealthTech and Medicines guidance
Greater demonstrable impact
Freeing up NHS therapist hours
Evidence shows that NICE-recommended digital therapies for depression and anxiety could free up thousands of NHS therapist hours – 6,000 hours per 1,000 people.
Boosting Access to Cancer Treatment
We have made six times more lung cancer treatment recommendations over the past 10 years than in the previous decade.
Around 5,000 blood cancer patients could benefit from 13 treatments recommended by NICE in 2024, the largest number of positive recommendations in this area in a single year.
Uptake of medicines in the NHS
73% of the latest NICE recommended medicines had increased use in the NHS in 2024 compared to 2023, including medicines for cancer, asthma and MS.
Clinicians’ guidance of choice
68% of UK healthcare practitioners said that NICE products are their guidance of choice when making decisions about care and 82% use NICE guidance at least once a month.
10

## Slide 11: Performance against KPIs
 | Key Performance Indicator (KPI) |  | 2024/25 outturn | 2024/25 target | 2023/24 outturn | Change since 23-24
Relevant | % of positive decisions made by the Prioritisation Board align to key NHS and social care priorities, including those described in our annual Forward View |  | 74% | 90% | N/A - new indicator | 
 | 95% of responses to Regulation 28 reports, Health Services Safety Investigation Body (HSSIB) safety recommendations and safety alerts within specified and/or statutory timeframes |  | 100% | 95% | 95% | 5 percentage point (pp) improvement
Timely & High Quality | Medicines - Mean time between marketing authorisation and NICE recommendation to fall from 452 days (optimal and divergent) |  | 335 days ​ | Improvement on 23-24 baseline​ | 452 days | 26% improvement
 | Medicines - Median time between marketing authorisation and NICE recommendation to fall from 322 days (optimal and divergent) |  | 328 days ​ | Improvement on 23-24 baseline​ | 322 days | 2% slower
 | Medicines - Mean time between marketing authorisation and NICE recommendation (optimal) |  | 48 days​ | 90 days ​ | 36 days | 33% slower
 | Medicines - Median time between marketing authorisation and NICE recommendation (optimal)​ |  | 44 days​ | 90 days ​ | 43 days | 2% slower
 | Medicines - Mean time between marketing authorisation and NICE recommendation (divergent)​ |  | 410 days​ | Improvement on baseline 23-24​ | 540 days | 24% improvement
 | Medicines - Median time between marketing authorisation and NICE recommendation (divergent)​ |  | 413 days​ | Improvement on baseline 23-24​ | 365 days | 13% slower
 | Medicines - Percentage of optimal topics published in 2024/25 |  | 21%​ | Improvement on 23-24 baseline​ | 17.5% | 3.5 pp improvement
 | HealthTech - Mean time to publish HealthTech guidance to fall from 490 days​ |  | 437 days​ | Improvement on 23-24 baseline​ | 490 days | 11% improvement
 | HealthTech - Median time to publish HealthTech guidance to fall from 402 days |  | 400 days​ | Improvement on 23-24 baseline​ | 402 days | 0.5% improvement
 | Centre for Guidelines – percentage of quality standard updates published alongside guideline updates ​ |  | 100%​ | 30%​ | N/A - new indicator | 
 | Percentage of Technology Appraisals (TAs) retrospectively incorporated into guidelines by end of 24/25​ |  | 35% | 33% | N/A - new indicator | 
Usable | Number of users accessing NICE website for guidance and advice​ |  | 18.8m | Increase on 23-24​ | 18.3m | 3% improvement
 | Clicks on guidance products from the NICE corporate website |  | 78,700​ | 95,700 | 83,200 | 5% reduction
Impactful | All agreed priority areas have targeted implementation support package in place |  | 3​ | 5​ | N/A - new indicators | 
 | New partnerships (including Voluntary and Community Sector organisations) to amplify the impact of NICE guidance in agreed priority areas. ​ |  | 5​ | 5​ |  | 
Brilliant Org | Media coverage of NICE that is positive in sentiment​ |  | 81%​ | 80%​ | 80% | 1 pp improvement
 | Media coverage that is generated by NICE includes at least one NICE key message​ |  | 52%​ | 60%​ | 54% | 2 pp reduction
 | Workforce representation | Ethnic minority staff | 21% | 20.3% | 18.21​% | +2.79pp
 |  | Staff with a disability | 11% | 10.44% | 9.49% | +1.51pp
 |  | LGBTQ+ staff | 9.1% | 9.17% | 8.34% | +0.76pp
 | Number of informal resolutions |  | 56 | 32 (50% increase) | 21 | 166% increase
 | Financial position​ |  | £2.35m underspend​ | No deficit, Surplus <£1m​ | Surplus <£1m | -

## Slide 12: Performance against milestones
Area | Milestones | Status
Relevant | Common prioritisation framework published following public consultation and agreement with system partners​ | Delivered
 | NICE’s Prioritisation Board launched​ | Delivered
 | Prioritisation Board’s forward look published​ | Delivered
 | Single horizon scanning function operational, linking with external providers​ | Delivered
 | Agreed an approach for recognising guidance from other organisations in areas where NICE does not produce guidance ​ | Delivered
 | Consulted on any identified changes to routing criteria for Highly Specialised Technology Appraisals​ | Delivered
Timely and High Quality | Start routinely incorporating relevant medicine technology appraisals in guidelines​ | Delivered
 | Understood baseline and opportunities for improvement in guidance producing processes​ | Delivered
 | Rolled out digital tools that support planning and identified future planning/scheduling needs​ | Delivered
 | Aligned and digitised some key steps in guidance producing processes​ | Delivered
 | Reviewed the use of the severity modifier in medicines evaluation and identified remedial actions if needed​ | Delivered
 | Updated methods for assessing health inequalities in guidance production​ | Delivered
 | Expanded HTA Lab capacity in line with new VPAG funding and delivered insightful outputs supporting high quality guidance​ | Delivered
 | Launched 8 Late-Stage Assessment topics​ | Delivered
 | Consulted (with NHSE) on a MedTech rules-based pathway​ | Delivered
Usable | Complete migration to new corporate website​ | Delayed
 | Complete proof of concepts with semantic data model to inform next steps of knowledge platform​ | Delivered
 | Agree standardised wording and structure for recommendations​ | Delivered
Impactful | Developed and implemented a fairer payment policy for involvement and engagement activity​ | Delivered
 | Routine reporting of prioritised uptake measures in plan​ | Delivered
 | Joint plans in place to amplify the impact of NICE guidance through priority partnerships ​ | Delivered
 | 5 implementation support packages initiated to address agreed priority areas ​ | 3 Delivered
 | Programme of shared learning in place, connecting practitioners and commissioners to implementation best practice​ | Delivered
 | Developed and tested impactful approaches for involving people and communities in developments in all new prioritised guidance​ | Delivered
Brilliant Organisation | Launched a new Equality, Diversity and Inclusion Roadmap including new objectives to improve staff experience and representation ​ | Delivered
 | Rolled out Power-BI enabled detailed financial forecasting and scenario planning to increase accuracy of forecasts and engage operational teams ​ | Delivered
 | Fully embedded finance business partnering to improve financial input into directorate decisions​ | Delivered
 | Completed a successful office move to our new Manchester office​ | Delivered
12

## Slide 13: NICE’s Business Plan for 2025/26

## Slide 14: How we currently deliver NICE’s Aims
Timely and High Quality | NICE delivers high quality guidance to the system through Technology Appraisals, Highly Specialised Technology Appraisals, Health Technology Evaluations, Guidelines, and Quality Standards NICE is one of the fastest HTA agencies globally. According to analysis by EFPIA, England has the 5th quickest time from central approval to availability out of 36 European nations Successful challenges of NICE findings are rare, and 79% of practitioners agree that NICE is scientific, rigorous and evidence-based NICE’s Health Technology Assessment Innovation Laboratory (HTA Lab) ensures that our methods and processes are fit for purpose for evaluating future innovations NICE and the MHRA are working closely to decrease the time between marketing authorisation (MA) and medicines evaluation guidance, and are considering options for closer collaboration
Relevant | Our Prioritisation Board ensures that we prioritise those areas of guidance development and delivery that will have the greatest impact on the health and care system NICE’s Horizon Scanning and Topic Intelligence functions ensure that NICE’s Prioritisation Board is aware of the innovations that will have the greatest impact on the health and care system so they can be prioritised
Usable | We deliver content and guidance products that help our practitioners, providers and commissioners make decisions: at point of care, by staying up to date and complying with latest advice
Impactful | We build and maintain partnerships with organisations and users of our guidance to ensure it is used by practitioners, providers and commissioners We engage with the health and care system to understand and address barriers to adoption and uptake We routinely collect guidance uptake data and system intelligence to inform areas for guidance update or improvement
Brilliant organisation | We look after our people, including through wellbeing initiatives, training, recruitment, and resolution of issues We carefully manage our budget to ensure we deliver the best possible value to the taxpayer We support NICE’s communications to broaden NICE’s influence and drive staff engagement We ensure we have effective, resilient and secure underpinning infrastructure to complete day-to-day activity
14

## Slide 15: 1. High quality, timely guidance: How we will go further in 2025/26
Project | Scope
Improving Timeliness | This programme of work will improve the timeliness of guidance production across guidelines, health tech and medicines whilst maintaining the quality of our guidance. We also aim to improve staff engagement and increase throughput of guidance producing centres. Improved timeliness will be achieved through standardising and improving processes across the guidance producing centres including the guidance producing ‘services’: topic management, committee management, stakeholder management, guidance generation, content creation, generation and use of management of information
Friction free pathway | This programme of work will look to identify areas where NICE, the MHRA and NHSE can work more closely, including sharing technical and operational information between NICE and MHRA, to decrease the time between MHRA marketing authorisation and NICE medicines evaluation guidance. Following identification of potential synergies, NICE, MHRA and NHSE will develop specific policy ideas to increase collaboration. We will launch pilot/s of initial areas of increased collaboration by the end of 2025/26.

## Slide 16: 1. Providing high quality, timely guidance: KPIs
*An error is defined as an issue that significantly changes a recommendation substantially (e.g. from recommended to not recommended), could cause harm or other major issue that could damage NICE's recommendation. The measure is captured at final product level (guideline, quality standard or indicator new or update). This measure is not intended to capture rewording of recommendations to improve clarity or other minor changes or updates (e.g. updating links etc).
KPI grouping | Indicator | Target (25/26) | Baseline | Reporting frequency
Timeliness of medicines evaluation guidance | Proportion of final guidance published within 240 working days of Invitation to Participate | 60% for new topics starting from April 2025 | 44% | Monthly
 | Proportion of final guidance published within 12 months of Marketing Authorisation | 50% | 57% | Monthly
Quality of TAs | Confidentiality Breaches (Medicines) | Tolerance of 12 | 16 | Monthly
Timeliness of Health Technology Evaluations (HTEs) | Proportion Health Tech moving from starting to finishing guidance within 9 months | 35% | 0% (10 months mean) | Monthly
 | Proportion of Health Tech topics moving from referral to Prioritisation Board (PB) decision within 66 working days | 50% | 50% | Monthly
 | Proportion of Health Tech Evaluations moving from Prioritisation Board decision to start of guidance development within 66 working days | 40% | 0% (5 months mean) | Monthly
Quality of HTEs | Confidentiality Breaches (HealthTech) | Tolerance of 6 | 6 | Monthly
Timeliness of Guidelines | Mean time for development of new guidelines or large guideline updates for topics starting 25/26 | 18 months | 0% (34 months average) | Monthly
 | Proportion of medium guideline topics published within 13 months of development starting from April 2025 | 50% | 0% (17.5 months mean) | Monthly
 | Proportion of small guideline updates published within 7 months of development starting for new topics from April 2025 | 50% | 0% (10 months mean) | Monthly
Quality of Guidelines | Proportion of guidelines, quality standards or indicators with errors* (at product level) published in 2025-26 | 0 | 0 YTD | Monthly
Timeliness of Quality Standards | Proportion of Quality Standards (new, updates and alignments) published at the same time as the associated guideline | 80% | 60% | Monthly

## Slide 17: 2. Relevant guidance: How we will go further in 2025/26 (1 of 2)
Project | Scope
Rules Based Pathway | Work with DHSC and NHSE to develop a clear, consistent, standardised and streamlined rules-based approach to HealthTech evaluations and adoption, including: Horizon scanning and demand signalling: Ensure evolving horizon scanning functions and demand signalling identify relevant topics for NICE evaluation. Topic intelligence and selection: Determine and establish strategic engagement for topic referrals, including across NHSE. Streamline and establish information and decision flows from topic referral to selection. Regulation and standards: Determine approach and checkpoints for due diligence of regulatory requirements and standards across pathway. Identify opportunities to streamline, reduce duplication and provide clarity for stakeholders Assessment and evidence generation: Determine any changes to assessment processes in light of commercial development and TA funding requirement. Provide clarity on definitions of value and approach to evidence generation. Commercial and procurement: Develop approach and checkpoints for commercial gateways and feasibility assessments to help shape price and run procurement in parallel with guidance development. Routes to reimbursement: Identify relevant routes to reimbursement and determine mechanisms to transact guidance linked with commercial mechanisms. Adoption and benefits realisation: Determine list of options and tools to support adoption and improve benefits realisation which need to be applied in different scenarios to enable effective scale and spread.
Improve Approach to Funding Variations (FVRs) | Review the current approach for dealing with funding variations (FVRs); and consider areas that need to be amended and strengthened: Facilitate the consideration of specific areas that will support an effective process, for example NICE’s position on the eligible population, duration for implementation, clinical prioritisation and further evidence generation if this is required. Develop a consistent, transparent and robust process for managing future funding variation requests. Confirm support from DHSC, and whether ministers wish to make any changes to current legislative arrangements relating to FVRs. Engage NHSE with a view to working collaboratively to identify relevant service and delivery models ahead of each potential FVR.
17

## Slide 18: 2. Relevant guidance: How we will go further in 2025/26 (2 of 2)
Project | Scope
Whole Lifecycle Approach | Incorporation: Continue incorporation of TAs into guidelines, aiming for 200 TAs considered for incorporation in 25/26 Updating guidance: Engage with a stakeholder advisory group to understand methods and process updates required to be able to keep our guidance up-to-date across our portfolio of products Retiring guidance: Develop an aligned approach to retiring out-of-date guidance, starting by looking at options for retiring recommendations in our clinical guidelines Biosimilar taskforce: Develop our strategy to address introduction of biosimilars/generic medicines and engage with the biosimilar taskforce Prioritisation: Develop a process for surveillance and prioritisation that focuses on updating and retiring guidance in topic areas where there's most potential to maximise population health, including expanding access to treatments or releasing cost savings to reinvest elsewhere Future model: Design and cost the future working model for a whole lifecycle approach to developing and maintaining up-to-date guidance that meets our users’ needs. Explore incorporation of HealthTech into guidelines, starting with mapping all HealthTech guidance to the relevant guidelines
Progress AI Statement of Intent | The following workstreams are in scope for 2025/26, building on the Statement of Intent for Artificial Intelligence (AI) at NICE: Policy & Strategy: Develop NICE's AI strategy to deliver on Statement of Intent, interfacing with the national policy landscape Partnership: Establish external partnerships to enable knowledge exchange and upskilling Science & Methods: Further build scientific collaborations to understand the applications of AI approaches for NICE. Identify areas for potential methods update. Implementation: Test and pilot AI methods and systems that support information management, including the use of AI in systematic literature reviews. Assess cyber risk for AI as a tool. DIT will provide supporting technology.

## Slide 19: 2. Relevant guidance: KPIs
KPI grouping | Indicator | Target (25/26) | Baseline | Reporting frequency
Relevance of NICE guidance | Proportion of primary users who report that guidance is relevant | 80% by Dec 2025 | 76% | Annually
 | Number of TAs considered for incorporation into guidelines since start of 24/25 | 383 (200 in 25/26) | 183 | Monthly
 | Proportion of positive decisions made by the Prioritisation Board that align to key NHS and social care priorities, including those described in our annual Forward View | 90% | 74% | Monthly
 | Proportion of primary (NHS) users who report that they agree or strongly agree that NICE guidelines include the assessments of related medicines and HealthTech products | Improvement on Q1 baseline | Baseline to be established in Q1 | Quarterly
 | Proportion of Prioritisation Board clarifications resolved at stage 1 (excluding HST) | 80% | 50% | Monthly
Increased focus on HealthTech | Number of Technology Appraisals launched for HealthTech | 2 in 2025/26 | N/A | Quarterly

## Slide 20: 3. Usable guidance: How we will go further in 2025/26
Project | Scope
Implementation of a platform to enable guidance content management and publication | We will implement a new content creation, curation & product publication and syndication service, underpinned by a knowledge platform by: Specifying, delivering and implementing a knowledge platform technical solution Reengineering structured guidance content / recommendations to enable content management in a new system This includes: Developing an approach to structured content creation and storage informed by the semantic data model proof of concept developed with Amazon Web Services (AWS) and delivering a data structure foundation and technology solution that we can build upon Developing a business case and other governance materials (including GDS assessment / procurement) including evaluating the outcomes and benefits to determine the value and technology approach Preparing a procurement strategy for digital solutions for content creation, curation and product publication Developing an approach to Information Management (informed by the semantic data model) that can be applied to all guidance content (existing and new) Testing and trialling new technology and developing training and roll-out plans. Developing and implementing a migration plan to new technology for existing guidance content Implementing structured recommendations across all guidance in the existing publishing system and testing new product formats

## Slide 21: 3. Usable guidance: KPIs
KPI grouping | Indicator | Target (25/26) | Baseline | Reporting frequency
Usability of published guidance | Proportion of our primary users who report that NICE guidance is usable | 80% by Dec 2025 | 78% | Annually

## Slide 22: 4. Impactful guidance: How we will go further in 2025/26
Project | Scope
Single programme of support for guidance uptake | Develop a joint programme with aligned outputs (tools, resources, and interventions) across five teams across NICE (national implementation, system implementation, people and communities, medicines optimisation, and resource impact assessment) to improve the uptake of NICE guidance for commissioners, providers, and practitioners in priority areas. Create support packages in priority areas to support the uptake and adoption of NICE guidance, including guidelines, medicines and HealthTech. Refresh NICE’s engagement approach with the health and care system, including Integrated Care Boards and through new and existing networks. Develop and deliver outcomes-based partnerships in the improvement system to align our efforts to improve guidance uptake. Agree the prioritised topics, informed by data and intelligence, that will deliver the improvement KPI and have greatest impact.

## Slide 23: 4. Impactful guidance: KPIs
KPI grouping | Indicator | Target (25/26) | Baseline | Reporting frequency
Improved uptake of NICE guidance | Proportion of all medicines included in the innovation scorecard showing annual increased use * | 70% | 73% | Bi-annually
 | Proportion of agreed quality standard measures in priority areas showing improved uptake | 75% | - | Bi-annually
* Medicines in the innovation scorecard portfolio changes bi-annually

## Slide 24: 5. Brilliant organisation: How we will go further in 2025/26 (1 of 2)
Project | Scope
Build Financial and Commercial Agility | Reduce NICE's exposure to fixed costs and changes in funding/income through a clear commercial strategy, more flexible contracting approach, and enhanced financial management. Focus on making best use of available funding to deliver our core objectives through more flexible resourcing and contracting, enabling the organisation to adjust to changing priorities, address pressures and capitalise on new opportunities. Develop a strategy setting out our ambition and approach to generating commercial and non-GIA income. The strategy will bring together and align our approach to existing income generation and identify any new areas to explore and will be developed alongside the new international strategy and ongoing development of NICE Advice.
Strengthen NICE’s Reputation and Influence | Broadening our development of communications to cover a wider range of corporate issues beyond individual guidance decisions. We will proactively identify priority topics that would benefit from simple, clear articulation of NICE’s organisational position and develop a narrative for each – which can then then be used to underpin the development of other kinds of content (e.g. key messages for the media, long reads, thought leadership pieces, briefing documents, slide decks). Increasing focus on external placement of storytelling content in a wider range of third-party channels. Channels in scope will include trade press and journals, stakeholder/membership organisations’ bulletins, newsletters and social media channels, third-party blogs and podcasts on which we can guest-blog/appear, major domestic conferences in the health and care/life sciences sectors at which we could seek speaking platforms Launching a year-long brand marketing and content plan aimed at nurturing positive perceptions of NICE. Beginning with a brand strategy ‘health check’ likely to result in a light-touch update of the brand strategy and corporate key messages. After this we’ll deliver 1 piece of brand-focussed content per quarter for sharing on owned/earned channels. And there’ll be a paid brand campaign aimed at health care practitioners in Q3. Completing the corporate website migration to maximise our ability to deliver storytelling content on this channel and to improve routes into guidance.
24

## Slide 25: 5. Brilliant organisation: How we will go further in 2025/26 (2 of 2)
Project | Scope
Embed Improvement into our Ways of Working | Strategic Provider: Bringing in a strategic provider to help embed improvement at all levels. This will be a suite of practical learning and work that will support leaders and teams to grow and practice with improvement tools and methods. Knowledge and Skills: Implementing a dosing approach to building different levels of improvement skills, including developing self-directed training/resources and bitesize quality improvement training materials; Continuous Quality Improvement Coaches: Enhance the role of change agents to include improvement coaching to support continuous quality improvement projects in each directorate; including developing a training programme for quality improvement coaches. Building Continuous Quality Improvement Communities: Directorate quality improvement forums to coordinate and resource local improvement activity Tracking and Measuring CQI Impact: Procuring software/tools to help track improvement projects. Embedding the use of timeseries charts for improvement, planning and standard work. Embedding use of Continuous Quality Improvement: Priority programmes, directorates and staff network to be supported to use the CQI method on what matters to them e.g. linked to an annual priority, a complex recurring issue, etc. Development of collaboration spaces: Partner with Workforce and Facilities Management to further develop spaces for people to collaborate on improvement work and use visual management boards to communicate effort and progress.
24

## Slide 26: 5. Brilliant organisation: KPIs
KPI grouping | Indicator | Target (25/26) | Baseline | Reporting frequency
Financial stability | Financial deficit/surplus | Surplus <£1m / no deficit | £2.35m surplus (24/25) | Monthly
 | Full-year revenue forecast accuracy | Full-year outturn within 1% of full-year forecast at Month 6 | Actual M12 position was 3.6% variance to M6 forecast, largely attributable to uncertainty throughout the year relating office move costs (the forecast variance was 0.7% if these office move costs are excluded) | Annual
Embedding improvement | Proportion of staff reporting that they feel empowered to make improvements | 75% | 67% | Quarterly
NICE maintains a strong reputation amongst key stakeholders | Favourability rate among our core audience | 80% | 76% | Annually
 | Proportion of media coverage generated by NICE that contains at least one key message | 58% | 54% | Monthly
 | Proportion of media coverage that is positive in sentiment | 80% | 79% | Monthly

## Slide 27: Additional KPIs on the health of the organisation
KPI grouping | Indicator | Target (25/26) | Baseline | Reporting frequency
Staff levels and availability | Vacancy rate | <6% | 7.1% | Monthly
 | Voluntary turnover rate | <= 10% | 7.9% | Monthly
Staff wellbeing | Proportion of staff who recommend NICE as a place to work | >=80% | 70% | Bi-annually
 | Proportion of colleagues experiencing bullying or harassment | <=6% | 7% | Bi-annually
 | Proportion of colleagues experiencing discrimination | <=5.5% | 6% | Bi-annually
Leadership and communications | Proportion of FOIs responded to within 20 working days | 90% | 98% | Monthly
 | Proportion of Parliamentary Questions responded to within the requested timeframe | 90% | 98% | Monthly
 | Staff agree they understand NICE’s purpose and their role in it | 4.1/5 | 4.0/5 | Monthly
 | Staff agree they feel informed about what is happening at NICE | 4.1/5 | 4.0/5 | Monthly
Cyber security and compliance | Cyber incidents | 0 | 2 | Monthly
 | % Level of Key System Availability | 99.9% | 95% | Monthly
 | Proportion of staff completing cyber training | 90% | 88% | Monthly
 | Proportion of staff completing mandatory training | >=85% | 80% | Monthly
26

## Slide 28: NICE’s Budget for 2025/26

## Slide 29: 2025/26 Budget
The following assumptions have been made in setting the 2025/26 budget, as shown in the table.
Total DHSC RDEL funding of £64.7m. This is inclusive of
  Administration RDEL funding of £51.5m for the majority of our statutory functions.
  Programme RDEL funding of £8m for specific programmes (BNF procurement and some HealthTech evaluation activities).
  Project funding to be transferred from the VPAG investment facility (£3.7m).
  Ring-fenced funding for depreciation charges on our assets and leases.
Technology Appraisal and HST income is planned to be £13.5m.
Pay budgets assume a 2% pay award in 2025/26 and include the impact of changes to Employer’s National Insurance costs.
Savings and modelling of expected vacancy / turnover rates have been applied to both pay and non-pay budgets to deliver a balanced budget with reserves available to enable investment.
2025/26 Sources and Application of Funds | Budget £000
DHSC Funding (RDEL) – Baseline | 59,529
DHSC Funding (RDEL) – VPAG facility | 3,650
Ring-fenced RDEL funding for depreciation | 1,512
TA/HST cost recovery | 13,530
NICE Advice | 4,322
Other income | 9,973
Total sources of funding | 92,516
Pay costs | 66,615
Non-pay costs | 23,773
Ring-fenced costs (Depreciation) | 1,512
Reserves | 616
Total baseline expenditure | 92,516

## Slide 30: 2025/26 Budget – Risks and Planning
There are several uncertainties in the financial plan for 2025/26. These include:
The budgets were set before the conclusion of SR phase 2 and the resource / financial implications of NICE commitments within the NHS 10-year plan being finalised. Whilst the impact of these is most likely to be felt in financial years 2026/27 onwards, we may need to make decisions to repurpose resource during 2025/26 which will affect the financial position.
Revenue from charges for assessments under the Technology Appraisal and HST programme can vary due to fluctuations in demand and changes to scheduled timelines. The income target of £13.5m reflects best estimates of throughput in 2025/26, taking into account organisational change within the Medicines Evaluation programme and the impact that adopting a whole lifecycle approach could have on income generation.
Most of our staff are on NHS Agenda for Change pay. Planning guidance issued by DHSC stated an assumption of 2% in 2025/26, but the actual award is not yet known. It is expected that the cost pressure will be covered by additional funding from DHSC.
There is a risk of slippage or cost pressures in budgeted spend on addressing technology debt issues and digital projects, such as implementing a knowledge platform solution, and organisational development projects, such as the timeliness programme. The priority project to build financial and commercial agility is looking at ways to deliver these projects (and other projects or opportunities) in a flexible way that enables the organisation to ramp up delivery or slow down spend depending on the financial position that develops through the year.