## Instructions
WELL™ Performance Verification Punch-List
WELL v2 ¦ Q2 2026
How to Use This Tool
This punch-list outlines specific action items that project teams should complete to prepare for performance verification. Review the punch-list at least one month prior to the scheduled date of performance testing to confirm all necessary steps are on track. Conduct a final review the day before testing to confirm readiness. The concept-specific tabs provide preparation guidance for each WELL strategy requiring on-site testing. WELL strategies may require additional verification methods beyond what is listed. For full details on performance testing protocols, consult the WELL Performance Verification Guidebook. Note on photographs: Some strategies require on-site photographs for verification. Photographs may be taken by a WELL Performance Testing Agent (PTAgent) as part of performance verification, or by a member of the project team for submission during documentation review. Confirm with your PTAgent which strategies are within scope for on-site photography prior to the testing date.
Quick Start: Preparation Timeline
1 month before testing → Review all concept tabs. Confirm all Feature strategies marked 'Pursuing: Yes' are on track. 2 weeks before → Attend the pre-performance verification call with your PTAgent to align on schedule, duration, site access, and any special requirements. 1 week before → Notify occupants, confirm site access for all parties, check for scheduling conflicts (events, cleaning, drills), and complete a walkthrough against this punch-list. Day before → Final walkthrough. Alert your PTAgent immediately of any incomplete items.
General Preparation — WELL Core Projects
Scope of Performance Testing for WELL Core projects: For WELL Core projects, at least 2.5% of the total building floor area must be available for performance testing for certain preconditions as shown in the PVGB. The available testing area must include all common areas and spaces directly under the control of the building management team. If common areas and spaces under owner control comprise less than 2.5% of the total building floor area, the project must supplement with tenant spaces to reach this threshold. Testing in leased spaces in these cases can take place before or after tenant occupancy. Some performance-based optimizations explicitly state that they require testing in tenant spaces to be awarded. The project is responsible for identifying and communicating to the WELL Performance Testing Agent (PTAgent) which particular spaces are available for testing. The following requirements must be met in order to have performance testing occur: 1. Ensure building construction and commissioning are complete prior to scheduling performance testing: Have all base building construction punch list items been completed? (Note, interiors projects do not need to be complete but should not be actively under construction. Construction within the building, even if outside of the project boundary or WELL Core scope, may impact environmental parameters that will be measured during on-site testing). • All painting is complete • All caulking/adhesives are complete • All carpet tiles and rugs are installed • All flooring finishes are complete 2. At least two weeks prior to the scheduled performance testing, project teams should attend the pre-pv call (typically scheduled by and led by the PTAgent) to discuss topics such as the overall testing schedule, duration of testing, access to the project, and any other requests from the PTAgent. 3. At least one week prior to scheduled performance testing, project teams should: • Notify all building occupants (if applicable) about upcoming performance testing. • Confirm the schedule with any additional parties that may need to be on site, including access to mechanical rooms (e.g., building operator, facilities manager). • Check to make sure no special events are planned during the testing (e.g., fire alarm drills, parties or events). • Check to make sure that the space has been cleaned, and that no cleaning will occur the day of performance testing. • Perform a walkthrough to verify all items identified in the check-list are complete. • Notify the PTAgent immediately if any punch-list items are not complete.
General Preparation — All Project Types Except WELL Core
The following requirements must be met in order to have performance testing occur: 1. Confirm that construction has been completed: Have all base building construction punch list items been completed? • All painting is complete • All caulking/adhesives are complete • All carpet tiles and rugs are installed • All flooring finishes are complete 2. Ensure that one month has passed since the issuance of the certificate of occupancy and that the space within the WELL project boundary is at least 50% occupied. • Note, if planned occupancy differs from maximum occupancy (e.g., summer vacation at a school building or reduced occupancy due to a public health emergency or natural disaster), projects may use the planned occupancy to calculate for this purpose. 2. At least two weeks prior to the scheduled performance testing, project teams should attend the pre-pv call (typically scheduled by and led by the WELL Performance Testing Agent (PTAgent)) to discuss topics such as the overall testing schedule, duration of testing, access to the project, and any other requests from the PTAgent. 3. At least one week prior to performance testing, project teams should: • Notify all building occupants (if applicable) about upcoming performance testing. • Confirm the schedule with any additional parties that may need to be on site, including access to mechanical rooms (e.g., building operator, facilities manager). • Check to make sure no special events are planned during the testing (e.g., fire alarm drills, parties or events). • Check to make sure that the space has been cleaned, and that no cleaning will occur the day of performance testing. • Perform a walkthrough to verify all items identified in the below list are complete. • Notify the PTAgent immediately if any punch-list items are not complete.
International WELL Building Institute, IWBI, the WELL Building Standard, WELL v2, WELL Certified, WELL AP, WELL EP, WELL Score, The WELL Conference, We Are WELL, the WELL Community Standard, WELL Health-Safety Rated, WELL Performance Rated, WELL Equity Rated, WELL Equity, WELL Coworking Rated, WELL Residence, Works with WELL, WELL and others, and their related logos are trademarks or certification marks of International WELL Building Institute PBC in the United States and other countries. Although the information contained in this document is believed to be reliable and accurate, all materials set forth within are provided without warranties of any kind, either express or implied, including but not limited to warranties of the accuracy or completeness of information or the suitability of the information for any particular purpose, and none of the parties involved in the creation of this document or the WELL Building Standard, and related resources and materials, including IWBI, its affiliates, and its and its affiliates’ respective owners, officers, directors or employees, assume any liability or responsibility to the user or any third parties for the accuracy, completeness, or use of or reliance on any information contained in this document, or for any injuries, losses, or damages (including, without limitation, equitable relief) arising from such use or reliance.
© 2026 International WELL Building Institute pbc. All rights reserved.
📋 Change Log ¦ Q2 2026 • Terminology: 'feature' / 'feature part' → 'WELL strategy' / 'strategy part' throughout, per OneWELL naming conventions. • Terminology: PTAgent and PTProvider spelled out in full on first use per IWBI style guide. • Structure: General preparation guidance for WELL Core and All Other project types consolidated into this tab (General tabs removed). • Content: Removed paragraph describing WELL Reviewer and PTAgent scopes (defined elsewhere); retained and clarified photograph guidance. • Structure: Added Quick Start preparation timeline. • Formatting: Applied Key tab color coding throughout — encoded fields (light blue), editable fields (light yellow), headers (light gray). • Concept tabs: Changelog moved to bottom of each tab. • Removed: Dashboard tab (non-functional); Mind tab (no strategies requiring performance testing). • Future enhancement (logged): Consider show/hide macro for photograph-only strategy tabs based on whether on-site photography is in PTAgent scope.

## Air
Air
General Guidance: 1. Ensure that testing can be conducted under regular project conditions. 2. Ensure that at least two to three weeks have passed since furniture installation. Note: If the space has been unoccupied for an extended period of time (e.g. due to a public health emergency or natural disaster), ensure that the HVAC systems are running, that the space has been flushed and that filters have been recently replaced. Note: Results can be impacted by dogs in the building, dry-cleaning pick up/drop off, idling cars, and occupant use of air fresheners. Refer to the Performance Verification Guidebook for information on sensor/testing requirements, required testing duration and compliance calculations.
WELL Strategy | Strategy Part | Verification Method | Preparation Guidelines | Type | Pursuing? | Project Team Notes
A01: Air Quality | 1. Meet Thresholds for Particulate Matter | Performance Test | Ensure testing is performed post occupany and under normal operating conditions. All testing and balancing and commissioning activities should be complete before testing air quality. Communicate normal operating hours for startup and shutdown of any HVAC systems related to the WELL Performance Testing Agent (PTAgent)'s plan/schedule for air testing. Ensure personelle with the ability to start or shut down HVAC systems are present during on-site testing if any before or after hours testing is agreed upon by the project team and the PTAgent. | Precondition
| 2. Meet Thresholds for Organic Gases | Performance Test | See preparation guidelines for this WELL strategy above. | Precondition
| 3. Meet Thresholds for Inorganic Gases | Performance Test | See preparation guidelines for this WELL strategy above. | Precondition
A02: Smoke-Free Environment | 2. Prohibit Outdoor Smoking | On-site Photographs | Ensure that signage about smoking bans and/or the health hazards of smoking are permanently mounted in outdoor areas; this may involve functional building entrances, operable windows, air intake and exterior spaces (including decks, patios, balconies, rooftops and other occupiable outdoor areas above ground level). | Precondition
A05: Enhanced Air Quality | 1. Meet Enhanced Thresholds for Particulate Matter | Performance Test | See guidance for A01: Air Quality | Precondition
| 2. Meet Enhanced Thresholds for Organic Gases | Performance Test | See guidance for A01: Air Quality | Precondition
| 3. Meet Enhanced Thresholds for Inorganic Gases | Performance Test | See guidance for A01: Air Quality | Precondition
A07: Operable Windows | 1. Provide Operable Windows | On-site Photographs | Ensure that the PTAgent has access to the windows. | Precondition
| 2. Manage Window Use | On-site Photographs | Confirm that the indicator light system and/or digital displays are functioning as intended and is measuring PM2.5, dry-bulb temperature and relative humidity. | Precondition
A08: Air Quality Monitoring and Awareness | 1. Install Indoor Air Monitors | On-site Photographs | Confirm that the indoor monitors with sensors are functioning as intended. | Precondition
| 2. Promote Air Quality Awareness | On-site Photographs | Confirm that the indoor air quality data is available to the PTAgent via displays or hosted on a website or phone application. | Precondition
A09: Pollution Infiltration Management | 1. Design Healthy Entryways | On-site Photographs | Confirm that entryway walk-off systems and appropriate doorways have been installed. The following guidance is applicable to projects with Outdoor Sports Areas: Ensure that the PTAgent has access to the inbetween indoor and outdoor sports area. | Precondition
A10: Combustion Minimization | 1. Manage Combustion | On-site Photographs | Ensure that signage restricting idling with vehicle engines has been installed in all pick-up, drop-off and parking areas controlled by the project. | Precondition
A11: Source Separation | 1. Manage Pollution and Exhaust | On-site Photographs | The following guidance is applicable to projects with Commercial Kitchen Spaces OR Dwelling Units: Ensure that the PTAgent has access to the pollution and exhaust systems. | Precondition
A12: Air Filtration | 1. Implement Particle Filtration | On-site Photographs | Ensure that the PTAgent has access to the mechanical system(s) to verify air filtration and to check for signs of mold growth. | Precondition
A13: Enhanced Supply Air | 1. Improve Supply Air | On-site Photographs | Ensure that the PTAgent has access to the air purification system(s) and the mechanical air system(s). | Precondition
A14: Microbe and Mold Control | 1. Implement Ultraviolet Treatment for HVAC Surfaces | On-site Photographs | Ensure that the PTAgent has access to all cooling coils and drain pans within central air handling units. | Precondition
📋 Change Log ¦ Q2 2026: 'Feature' → 'WELL strategy'. 'PTAgent' spelled out on first use. Type column added (Precondition/Optimization). Yes/No/N/A dropdown on 'Pursuing?'. Key tab color coding applied. Blank prep guidance rows read 'See strategy guidance above'. Changelog moved to bottom.

## Water
Water
General Guidance: 1. Confirm that all plumbing fixtures have been installed, commissioned and flushed to prevent the introduction of extraneous particles or residues from pipes or fixtures into the water that may impact test results. 2. If filters (including replacement cartridges) or other water treatment devices have been installed, confirm that they have been installed and conditioned (i.e., sufficient water is flushed through the system) according to the manufacturers’ instructions. 3. Confirm the extent of faucets that can supply cold water. If faucets automatically mix hot and cold water, confirm if hot water can be turned off during testing. We recommend that tests should be take from these faucets using cold water, if possible. 4. Ensure that the WELL Performance Testing Agent (PTAgent) will have access to at least one drinking water outlet that delivers water of the same quality to that delivered to tenant spaces. Note: If the space has been unoccupied for an extended period of time (e.g. due to a public health emergency or natural disaster), ensure that pipes have been flushed. Note: Support water quality by flushing water lines/fixtures that have not been used in several days, remember that dispensers that are not plumbed will be tested (water bottles, water on tap-carbonated). Refer to the Performance Verification Guidebook for information on sensor/testing requirements, required testing duration and compliance calculations.
WELL Strategy | Strategy Part | Verification Method | Preparation Guidelines | Type | Pursuing? | Project Team Notes
W01: Water Quality Indicators | 1. Verify Water Quality Indicators | Performance Test | Ensure that the WELL Performance Testing Agent (PTAgent) has access to all applicable water fixtures (drinking water, handwashing, shower, bath and those used for cooking purposes in commercial kitchens). | Precondition
W02: Drinking Water Quality | 1. Meet Chemical Thresholds | Performance Test | Ensure that the PTAgent has access to water fixtures for drinking and/or cooking. | Precondition
W04: Enhanced Water Quality | 1. Meet Thresholds for Drinking Water Taste | Performance Test | Ensure that the PTAgent has access to water fixtures for drinking and/or cooking. | Precondition
W07: Moisture Management | 2. Design Interiors for Moisture Management | On-site Photographs | Ensure that the PTAgent has access to all hard-piped fixtures and water treatment devices that have waster or drain line. | Precondition
W08: Hygiene Support | 1. Provide Equipped Bathrooms | On-site Photographs | Ensure that bathroom furnishing and amenities are available. | Precondition
| 2. Provide Hands-Free Fixtures in Bathrooms | On-site Photographs | Ensure hands-free fixtures are available. | Precondition
| 3. Support Effective Handwashing | On-site Photographs | Ensure access to handwashing fixtures are available. | Precondition
| 4. Provide Handwashing Supplies | On-site Photographs | Ensure that: 1. Handwashing equipment have been installed and that signage with handwashing instructions is available. 2. Handwashing support is available, including fragrance-free soap and a hand drying method. The following guidance is applicable to projects with Commercial Kitchen Spaces and Dining Spaces: Confirm that signage directing occupants towards the nearest handwashing location at the entrance to all areas intended for food preparation and consumption. | Precondition
W09β: Onsite Non-Potable Water Reuse | 1. Implement Safety Plan for Non-Potable Water Capture and Reuse | On-site Photographs | Confirm that visual signage distinguishing potable from non-potable water is present, in addition to displays with safety and conservation information. | Optimization
📋 Change Log ¦ Q2 2026: 'Feature' → 'WELL strategy'. PTAgent first-use expanded. General guidance restored (was inadvertently removed in prior revision). Type column added. Yes/No/N/A dropdown on 'Pursuing?'. Key tab color coding applied. Changelog moved to bottom.

## Nourishment
Nourishment
General Guidance: 1. Confirm all foods and beverages sold or provided on a daily basis (or under contract with) the project owner are available and accessible to the WELL Performance Testing Agent (PTAgent). This includes any space used for the sale or provision of foods (i.e., food outlets), including but not limited to cafeterias, cafes, restaurants, kitchenettes, pantries, micro-markets, micro-kitchens, food kiosks, concession stands and vending machines within the project boundary. 2. Ensure that the PTAgent has access to all commercial dining and kitchen spaces.
WELL Strategy | Strategy Part | Verification Method | Preparation Guidelines | Type | Pursuing? | Project Team Notes
N01: Fruits and Vegetables | 2. Promote Fruit and Vegetable Visibility | On-site Photographs | Confirm that fruits and vegetables at all food outlets are prominently displayed. Ensure that fruits and vegetables are visible to the WELL Performance Testing Agent (PTAgent). | Precondition
N02: Nutritional Transparency | 1. Provide Nutritional Information | On-site Photographs | Ensure that total calories, macronutrient content and total sugar per serving or package is available for all packaged foods and beverages, including items in vending machines and self-service bulk foods. The following guidance is applicable to projects with Commercial Dining Spaces: Ensure calories are labeled for standard menu items at the point-of-decision. Additionally, confirm that macronutrient content is available upon request. | Precondition
| 2. Address Food Allergens | On-site Photographs | The following guidance is applicable to projects with Commercial Dining Spaces: Ensure that signage is present which prompts individuals to report any potential food allergies to food service staff. | Precondition
| 3. Label Sugar Content | On-site Photographs | The following guidance is applicable to projects with Commercial Dining Spaces: Ensure that standard menu items containing more than 25 g of sugar are identified at the point-of-decision by an icon along with an explanation of the icon and the health risks of high sugar intake. | Precondition
N04: Food Advertising | 1. Optimize Food Advertising | On-site Photographs | Confirm that a total of at least two different instances of nutritional messaging are available and that advertisements for food or beverages adhere to the requirements. | Precondition
N06: Portion Sizes | 1. Promote Healthy Portions | On-site Photographs | Confirm that food and beverage items reflect the menu requirements. The following guidance is applicable to projects with Commercial Dining Spaces where self-serve food is offered: Confirm dishware meets the WELL strategy requirements. | Precondition
N09: Special Diets | 2. Label Food Allergens and Intolerances | On-site Photographs | Ensure that the common food allergens and intolerances are labeled at point-of-decision for all foods and beverages. | Precondition
N10: Food Preparation | 1. Provide Meal Support | On-site Photographs | Confirm that at least one dedicated eating area contains all required, supportive amenities. The following guidance is applicable to projects with Dwelling Units: Confirm that all dwelling units contain all required, supportive amenities. The following guidance is applicable to projects with Guest Rooms: Confirm that all guest rooms contain all required, supportive amenities. | Precondition
N11: Responsible Food Sourcing | 1. Implement Responsible Sourcing | On-site Photographs | Ensure that sustainable and humane agriculture are is promoted at the point-of-decision. | Precondition
📋 Change Log ¦ Q2 2026: 'Feature' → 'WELL strategy'. Type column added. Yes/No/N/A dropdown on 'Pursuing?'. Key tab color coding applied. Changelog moved to bottom.

## Light
Light
General Guidance: 1. Confirm all light fixtures that contribute to achievement of the WELL strategies have been installed and will be turned on for performance testing. 2. For lighting control systems with settings that are only adjustable by a property manager or lighting consultant, ensure that an individual who has the ability and knowledge to adjust the system settings is available on-site (in the event that adjustments are necessary on site). 3. Light measurements are taken at night, so ensure that the building is accessible for testing and automatic dimming settings have been adjusted to represent light levels during regular hours. Refer to the Performance Verification Guidebook for information on sensor/testing requirements, required testing duration and compliance calculations.
WELL Strategy | Strategy Part | Verification Method | Preparation Guidelines | Type | Pursuing? | Project Team Notes
L02: Visual Lighting Design | 1. Provide Visual Acuity | Performance Test | Review this Reviewer Tip article. Confirm that all indoor and outdoor spaces within the project boundary have light fixtures that provide appropriate illuminance levels for the lighting reference guidelines selected by the project. For projects pursuing Option 2: Predetermined light levels, ensure that light levels meet the requirements for space types within the project. The following guidance is applicable to projects with Dwelling Units: Confirm that all kitchens and bathrooms within the dwelling units have light fixtures that provide appropriate illuminance levels for the lighting reference guidelines selected by the project. | Precondition
L03: Circadian Lighting Design | 1. Meet Lighting for Day-Active People | Performance Test | Confirm that all regularly occupied spaces have light fixtures that provide equivalent melanopic lux (EML) requirements. Lights should be turned on and, if applicable, programmed to meet levels at night as performance testing takes place after sunset. The following guidance is applicable to projects with Dwelling Units & Guest Rooms: Confirm that all dwelling units and guest rooms have light fixtures that provide equivalent melanopic lux (EML) requirements. Lights should be turned on and, if applicable, programmed to meet levels at night as performance testing takes place after sunset. If pursuing the strategy outlined in FAQ #194, ensure that a sufficient number of task lights are available for testing and note that the project team should be prepared to move and set-up the task lights at each station before the measurement is recorded by the WELL Performance Testing Agent (PTAgent). | Precondition
L05: Daylight Design Strategies | 2. Integrate Solar Shading | On-site Photographs | Ensure that all vertical transparent envelope glazing has solar shading systems that have been properly installed and programmed. | Precondition
📋 Change Log ¦ Q2 2026: 'Feature' → 'WELL strategy'. Type column added. Yes/No/N/A dropdown on 'Pursuing?'. Tab title trailing space removed. Key tab color coding applied. Changelog moved to bottom.

## Movement
Movement
General Guidance: 1. Confirm that a member of the project team is on-site to demonstrate design amenities that support Movement WELL strategies.
WELL Strategy | Strategy Part | Verification Method | Preparation Guidelines | Type | Pursuing? | Project Team Notes
V02: Ergonomic Workstation Design | 1. Support Visual Ergonomics | On-site Photographs | Confirm that all adjustable computer monitors and height-adjustable stands have been installed. For workstations where laptops are primarily used, confirm that the supplemental devices have been installed. | Precondition
| 2. Provide Height-Adjustable Work Surfaces | On-site Photographs | Confirm that at least 25% of all workstations can be adjusted by the user for both seated and standing work. | Precondition
| 3. Provide Chair Adjustability | On-site Photographs | Confirm that all adjustable chairs have been installed. | Precondition
| 4. Provide Support at Standing Workstations | On-site Photographs | Confirm that all standing support devices have been installed. | Precondition
V03: Circulation Network | 2. Integrate Point-of-Decision Signage | On-site Photographs | Ensure that motivational point-of-decision signage has been placed near the main building entrace, at the elevator banks and at stair entry points. | Precondition
V04: Facilities for Active Occupants | 1. Provide Cycling Infrastructure | On-site Photographs | Ensure that short-term and long-term bicycle parking is available for inspection, and bicycle maintenance tools are in place and available for inspection. | Precondition
V07: Active Furnishings | 1. Provide Active Workstations | On-site Photographs | Confirm that a sufficient percentage of active workstations have been installed. | Precondition
📋 Change Log ¦ Q2 2026: 'Feature' → 'WELL strategy'. Type column added. Yes/No/N/A dropdown on 'Pursuing?'. Key tab color coding applied. Changelog moved to bottom.

## Thermal Comfort
Thermal Comfort
General Guidance: 1. Ensure that spaces representative of typical occupied areas are available for testing. Refer to the Performance Verification Guidebook for information on sensor/testing requirements, required testing duration and compliance calculations.
WELL Strategy | Strategy Part | Verification Method | Preparation Guidelines | Type | Pursuing? | Project Team Notes
T01: Thermal Performance | 1. Provide Acceptable Thermal Environment | Performance Test | Review this Reviewer Tip Article. Ensure to document metabolic rate and clothing values before testing. Ensure that heating and cooling systems are fully functional and/or that naturally conditioned spaces are configured properly. The following guidance is applicable to projects with Commercial Kitchen Spaces: Ensure that the operative temperature meets the requirement. | Precondition
T04: Individual Thermal Control | 1. Provide Personal Cooling Options | On-Site Photographs | Confirm that personal cooling methods (e.g., thermostat, desk fan, cooling chair) are accessible. | Precondition
| 2. Provide Personal Heating Options | On-Site Photographs | Confirm that personal heating methods (e.g., thermostat, space heater, heated chair, blankets) are accessible. | Precondition
T06: Thermal Comfort Monitoring | 1. Monitor Thermal Environment | On-Site Photographs | Ensure indoor monitors and displays are functioning as intended. | Precondition
T07: Humidity Control | 1. Manage Relative Humidity | Performance Test | Ensure that the mechanical system is functioning as intended. | Precondition
T08β Enhanced Operable Windows | 1. Provide Windows with Multiple Opening Modes | On-Site Photographs | Ensure that operable windows are functioning as intended. | Optimization
📋 Change Log ¦ Q2 2026: 'Feature' → 'WELL strategy'. Type column added (β rows = Optimization). Yes/No/N/A dropdown on 'Pursuing?'. Key tab color coding applied. Changelog moved to bottom.

## Sound
Sound
General Guidance: 1. To the extent possible, ensure that testing occurs when the space is unoccupied or when the fewest number of people are on-site or nearby. 2. Furniture, furnishings and appliances: a. Confirm that all carpets and rugs have been installed. b. Confirm that all wall panels, ceiling tiles or acoustical panels have been installed. c. Confirm that cabinetry, credenzas, workstations and similar furnishings have been installed. 3. Operations and technology: a. Ensure that the project team or facility/office manager has the ability to operate HVAC system throughout. This designated representative may request that certain spaces be unoccupied during acoustics testing. Refer to the Performance Verification Guidebook for information on sensor/testing requirements, required testing duration and compliance calculations.
WELL Strategy | Strategy Part | Verification Method | Preparation Guidelines | Type | Pursuing? | Project Team Notes
S02: Maximum Noise Levels | 1. Limit Background Noise Levels | Performance Test | Confirm that the project team or other individual is available to operate the HVAC and sound maskings systems. The following guidance is applicable to projects with Dwelling Units & Guest Rooms: Confirm that the project team or other individual is available to provide access to relevant rooms. | Precondition
S03: Sound Barriers | 2. Achieve Sound Isolation at Walls | Performance Test | Confirm that the project team or other individual has the ability to operate HVAC systems. | Precondition
S04: Reverberation Time | 1. Achieve Reverberation Time Thresholds | Performance Test | Confirm that the project team or other individual has the ability to operate sound masking systems. | Precondition
📋 Change Log ¦ Q2 2026: 'Feature' → 'WELL strategy'. Type column added. Yes/No/N/A dropdown on 'Pursuing?'. Key tab color coding applied. Changelog moved to bottom.

## Materials
Materials
General Guidance: 1. Confirm that a member of the project team is on-site to demonstrate strategies that support Materials WELL strategies.
WELL Strategy | Strategy Part | Verification Method | Preparation Guidelines | Type | Pursuing? | Project Team Notes
WELL strategy X12: Contact Reduction | 1: β Contact reduction cues | On-site Photographs | Ensure that contact reduction strategies have been implemented and can be photographed. | Optimization
📋 Change Log ¦ Q2 2026: 'Feature' → 'WELL strategy'. Type column added. Yes/No/N/A dropdown on 'Pursuing?'. Key tab color coding applied. Changelog moved to bottom. Note: Tab contains one strategy (X12). Confirm completeness with Standard Development team.

## Community
Community
General Guidance: 1. Confirm that a member of the project team is on-site to demonstrate strategies that support Community WELL strategies.
WELL Strategy | Strategy Part | Verification Method | Preparation Guidelines | Type | Pursuing? | Project Team Notes
C13: Accessibility and Universal Design | 3: β Support Building & Neighborhood Wayfinding | On-site Photographs | Ensure that building information is provided meeting the WELL strategy requirements. | Optimization
📋 Change Log ¦ Q2 2026: 'Feature' → 'WELL strategy'. Type column added. Yes/No/N/A dropdown on 'Pursuing?'. Key tab color coding applied. Changelog moved to bottom.